## ALL WORKS (T&C) Annexure -15
| S.No. | S.No.of list from Deptt. Of Culture ( Ref. Secy. Culture D.O.No. 5-P&C (17/2003) dt. 1/3/2004 addressed to DG. | State | Project | Station | Client | Amount sanc-tioned | Date of A/A &E/S | Stipulated date of start | Stipulated date of Completion | Target date of completion | Financial Progress | Physical Progress | Remarks
| 1 | 144 | ASSAM | Pdg. Infrastructure locality at Moa Kamakhya Shakti Peet (PH-A) | Guwahati | Culture | 151.27 | 2003-10-01 | - | - | - | - | - | Site is yet to be handed over by the State Government. Scope of work changed/ reduced by Minister (Planning & Development) Govt. of Assam, in meeting held on 2.9.04 at Guwahati. Proposed drawings for toilet block etc. not acceptable to them and they have appointed their own Architect who will give drawings. Drawings awaited.
|  |  | ASSAM | Improvement of Infrastructure facility at Maa Kamakhya Shakti Peeth, Neelachal Hills, Kamakhya (PH-B). | Guwahati | Culture |  |  |  | - |  |  |  | Client accquired new site in Jan'04. Drawings & PE submitted to client. Approval/ sanction awaited.
|  |  | ASSAM | C/o Institute of Hotel Management at Guwahati | Guwahati | Culture | 1280.5 | 2002-02-01 | - | - | 2005-02-01 | 60 | - | Tender for Boys & Girls Hostel are under scrutiny. GMC yet to approve layout/bldg. Plan.
|  |  | ASSAM | (I) Earth filling & boudary wall | Guwahati | Culture | - | - | 2002-11-01 | 2003-09-01 | 2004-04-01 | 34.57 | 60% | Earth filling completed. Pile casting for boundary wall in progress.
|  |  | ASSAM | (ii) Admn. Cum Intt. Bldg. | Guwahati | Culture | - | - | 2003-08-01 | 2005-02-01 | 2005-02-01 | 84.42 | 26% | Foundation in progress. 1st floor slab completed.
|  |  | ASSAM | (iii) Boys Hostel | Guwahati | Culture | - | - | 2004-01-01 | 2005-05-01 | 2005-05-01 | 11.86 | 5% | Foundation in progress.
|  |  | ASSAM | (iv) Resdl.Qtrs. | Guwahati | Culture | - | - | - | - | 2005-07-01 | - | - | Work awarded. Test pile casted. Testing completed.
| 2 |  | ASSAM | C/o Institute of Hotel Management at Shillong | Shillong | Culture | 1334 | 1999-04-01 | - | - | - | - | - | New site was acquired by client in Jan. 04 and drawings as per new site conditions submitted to them in Feb. 04. Approval received recently with minor modifications. Modified drawings under preparation.
| 3 |  | ASSAM | C/o Resdl. Qtrs. For ASI at Shillong | Shillong | Culture | - | - | - | - | - | - | - | Client was requested to furnish detail requirements. Reply is awaited.
| 4 |  | ASSAM | Youth Hostel at Udaipur | Udaipur | Culture | 144.01 | 2004-08-01 | - | - | - | - | - | RPE for Rs. 2,33,85,600/- ws sent in 1/02. A/A &E/S is awaited.
| 5 |  | ASSAM | Youth Hostel at Churachandpur and Thoubal | Thaubla | Culture | - | - | - | - | - | - | - | Drgs. For these works have been prepared by MPHC. The work at these two locations have been kept in abeyance since the client deptt. has not conveyed any final decision about the works to CPWD.
| 6 |  | ASSAM | Youth Hostel at Bishnupur | Bishnupur | Culture | 202.6 | 2000-03-01 | - | - | - | - | - | Client is yet to give formal approval, whether this work is be done by CPWD.
| 7 |  | ASSAM | C/o Resdl qtrs for staff of NER center ASOI | Shillong | Culture | - | - | - | - | - | - | - | Approval still awaited from Client deptt.
| 8 | 21 | BIHAR | Dev. Work in Land around Kshatriya Kund at Lachhaur, Jamui (Bihar). | Jamui | Culture | 125 | 2002-05-01 | 2003-08-01 | 2004-02-01 | 2004-08-01 | 175.66 | 100 | Work completed. Tender amount was more than sanction. 6 km road length was in actua moret than sanctined length 5 km Pump to be installed. 1 tubewell was successful out of 4 bored.
| 9 | 22 | BIHAR | Development of work of Jain temple at Pawapuri, Bihar. | Pawapuri | Culture | 241 | 2002-01-01 | 2002-06-01 | 2002-10-01 | 2005-01-01 | 100.97 | 100 | Major civil work completed. Horticulture work awarded in 8/04. Electrical work in progress. Cable laying 75% over rahtways complete. Renovation of Ghans 2 nos. and 19 nos. marble henches are in progress.
| 10 | 23 | BIHAR | C/o Resdl. Qtrs. Nalanda. SH: C/o T-II 6 Nos. T-III-6, T-IV-12, T-VI-1 No. Nav Nalanda Mahavihara at Nalanda | Nalanda | Culture | 185.77 | 2000-04-01 | 2000-11-01 | 2001-11-01 | 2004-12-01 | 169.8 | 100 | Work completed.
1 | 11 |  | BIHAR | C/o Administrative Bldg. For Nav Nalanda Mahavihar at Nalanda | Nalanda | Tourism | 91 | 2002-04-01 | 2003-01-01 | 2004-06-01 | 2004-12-01 | 40.66 | 90 | To be completed in 12/04. Finishing work in progress.
| 12 | 24 | BIHAR | Improvement in riding quality of surface of NH- 82 & 83 for Biharsharif to Bodhgaya change 0 to 106 Km (a) Chainge 0-23 (b) Chainage 23-46 | Bodhgaya | Culture | 2207.74 | 2002-01-01 | 2002-10-01 | 2003-07-01 | 2004-03-01 | 916.86 | 90 | Work completed 7/03. Balance work in progress.
2 | 13 | 22 | BIHAR | Development of Maya-Sarovar at Bodhgaya | Bodhgaya | Tourism | 150 | 2002-12-01 | 2003-11-01 | 2004-05-01 | 2005-03-01 | 39.49 | 45 | Foundation work in progress. (I) civil work e.g. Boundary wall Plaza - I & 2, Green Room stage open Air Theatre under progress. The work of development of pond, pathway services plaza etc. alongwith part of boundary wall not taken up due to nonshifting of high school bldg,Matter has been taken up with district administration (i) Horticulture work started (iii) Electrical work just started.
3 | 14 | 23 | BIHAR | Development of meditation Park at Mahabodhi temple Complex Bodhgaya | Bodhgaya | Tourism | 75 | 2002-12-01 | 2003-04-01 | 2003-10-01 | 2004-08-01 | 80.15 | 100 | Work completed except part laying of water supply line. Drgs. Received from HUDCO in 8/04. Horticulture work completed.
4 | 15 | 24 | BIHAR | Signages | Bodhgaya | Tourism | 15 | 2002-12-01 | - | - | - | - | - | A/A & E/S for Rs. 15 lacs was received during Dec.2002. Drawings details have been received from HUDCO very recently for Bodhgaya. The work involves fixing of signages of stone as well as retro-reflective paint surfaces for facilitating access to airports, various buildings/ facilities etc. This is being taken up. Drawings for signages for other places awaited from HUDCO and could be taken up during completion stages of main works at other places. Partly in progress. Bodhgaya temple completed.
5 | 16 | 17 | BIHAR | Improvement of Abhishek Pushkarni at Vaishali. | Vaishali | Tourism | 75 | 2002-12-01 | 2003-05-01 | 2004-05-01 | 2004-12-01 | - | - | DE/NIT in process. Sanctioned estimate & amount does not mathc with drawing issued by HUDCO. DE under process to be submitted to client deptt for approval and revise sanction. ASI approval awaited.
6 | 17 | 21 | BIHAR | Development of Tourist facility Nodes at Nalanda | Nalanda | Tourism | 25 | 2002-12-01 | 2004-05-01 | 2004-08-01 | 2004-12-01 | 20.86 | 96 | Civil work completed. Horticulture & Electrical work is in progress.
7 | 18 | 19 | BIHAR | Re-development / improvement of Tourist facility at Kund area Rajgir | Rajgir | Tourism | 60 | 2002-12-01 | 2004-05-01 | 2004-12-01 | 2004-12-01 | - | - | Approved drg. From ASI received. Delay in receipt of approved issued from ASI. Tender to be called 9/04.
8 | 19 | 20 | BIHAR | Redevelopment / improvement of Bimbsara Avenue, Rajgir | Rajgir | Tourism | 50 | 2002-12-01 | 2004-04-01 | 2004-08-01 | 2005-02-01 | 1900-01-06 01:41 | 40 | Work is in progress.
9 | 20 | 18 | BIHAR | Re-development of Tourist facilities Nodes near Rope Way Station Rajgir, Bihar. | Rajgir | Tourism | 55 | 2002-12-01 | - | - | - | - | - | Drawings just received (7/04) from HUDCO. DE/NIT under process.
10 | 21 |  | BIHAR | Development works at Kundalpur Nalanda | Nalanda | Tourism | 18 | 2002-10-01 | 2003-03-01 | 2003-09-01 | 2004-04-01 | 16.27 | 100 | Works completed in Arl'04.
| 22 |  | BIHAR | Development works at Baso kund Vaishali | Vaishali | Culture | 452 | 2002-02-01 | 2003-03-01 | 2004-10-01 | 2005-03-01 | 206.71 | 60 | Project tobe completed in 3/05. Tender was called four times without any result. Now tender for ancillary structure to be splited and tender to be called soon. For road and path tender accepted.
| 23 | 13 | BIHAR | Upgradation of education facilities at JP Nagar Ballia | Ballia | Culture | 102.97 | 26.11.02 | 27.6.03 | 21.4.04 | 2004-05-01 | 5.62 | 80 | Work in progress.
| 24 |  | BIHAR | Renovation & refurbishment of the Halls & Corridors of Mahila Charkha Samiti, Kadamkuan, Patna for mounting the exhibition on Jayaprakash Narayan. | Patna | Culture | 7.32 | 2003-03-01 | 2003-07-01 | 2003-08-01 | 2003-10-01 | 7.3 | 100 | Completed. Exhibition photos also mounted on 8/9th Oct. 03.
| 25 |  | BIHAR | Memorial of Late Jayaprakash Narayan at Kadamkuan Patna | Patna | Culture | 42.26 | 2002-12-01 | 2003-05-01 | 2003-11-01 | 2004-10-01 | 31.83 | 100 | Work completed.
| 26 |  | BIHAR | Renovation works at Sarvodaya Ashram of Late Jayaprakash Narayan, Sokhodeora, Distt. Nawada. | Nawada | Culture | 107 | 2002-12-01 | 2003-05-01 | 2003-11-01 | 2004-06-01 | - | - | To be completed in Oct.-04
|  |  | BIHAR | SH: Udog Bhawan & Hostel | Nawada | Culture | - | - | 2003-05-01 | 2003-11-01 | 2005-01-01 | 36.32 | 95 | 50% Udog Bhawan flat part portion completed and handed over. Udog Bhawan and hostel for Balance. Roofing in progress. Work slowed down due to poor law and order condition.
|  |  | BIHAR | SH: JP Niwas & Jawahar Library Rajendra Bhawan & 4 Nos. Guest House. | Nawada | Culture | - | - | 2003-05-01 | 2003-11-01 | 2005-01-01 | 14.28 | 98 | Jawahar library, Rajendra Bhawan & 2 Nos. Guest House completed. JP Niwas work not yet taken up as its condition is very bad shape and removal of roof may lead to collapse of whole all leading to change in shape of structure & deviation of sanction. accordingly local client has been intimated. progress slowed down due to poor law and order condition.
|  |  | BIHAR | SH: Water Supply | Nawada | Culture | - | - | 2003-05-01 | 2003-09-01 | 2003-09-01 | 4.92 | 100 | Work Completed
|  |  | BIHAR | SH: Boundary wall | Nawada | Culture | - | - | 2003-07-01 | 2003-12-01 | 2003-12-01 | 22.95 | 100 | Work Completed
| 27 |  | BIHAR | Fencing over Dwarf wall at ASI's stie, Rajgir, Bihar. | Rajgir | Culture | 251.61 | 2003-09-01 | 2004-07-01 | 2005-07-01 | 2005-07-01 | 75.47 | 42 | Tenders reced on 15/3/04 and under scrutiny. Work to be completed in March 05. Work awarded in 7/04.
| 28 |  | BIHAR | Faculty building for Nav Nalanda Mahavihar at Nalanda | Nav Nalanda | Culture | 355.53 | 2004-04-01 | [5 empty] | Director NNM, Malanda approved. The Architectural drawings.in 8/04 Detailed arch drgs, awaited from SA Patna
11 | 29 |  | BIHAR | Development scheme for Bodhgaya (ph-II) in Bihar under scheme of destination development | Bodhgaya | Tourism | 462.53 | 2004-05-01 | [5 empty] | Sanction received recently in May,04. Architectural drawings awaited from HUDCO. Survey site plan sent to HUDCO on 21/6/04. Client yet to give possession of land of CPWD.
|  |  | BIHAR | a) Land scape development Kalchakra maidan | Bodhgaya | Culture | [7 empty] | Tender received and under process in CE's office.
|  |  | BIHAR | b) Traffic interchange Node-I | Bodhgaya | Culture | [7 empty] | Tender being received in Jan'05
|  |  | BIHAR | c) Bodh Gaya hatt near byepass main approach road. | Bodhgaya | Culture | [7 empty] | Work drg awaited from HUDCO.
|  |  | BIHAR | d) Shopping cum traffic interchange node near road along road along river. | Bodhgaya | Culture | [7 empty] | Tender being process. Tender to be called in 1/05.
12 | 30 |  | BIHAR | Development scheme for landscape development around of Malik Ibrahim Bayyu and temple surroundings at Bihar Sharif (Bihar) as part of Nalanda circuit. | Nalanda | Tourism | 134 | 2004-05-01 | [5 empty] | DE/NIT under process. Tender to be called in 1/05
|  |  | BIHAR | a) Construction/ Renovation of soon long and 5m wide stone pathway i/c 380 mm thick 400 mm high local stone masonry. | Nalanda | Tourism
|  |  | BIHAR | b) Intensive landscaping i/c pathway fencing. | Nalanda | Tourism | [7 empty] | DE under progress.
|  |  | BIHAR | c) c/o Toilet block | Nalanda | Tourism
|  |  | BIHAR | d) C/o 4 Nos. of Kiosk | Nalanda | Tourism
|  |  | BIHAR | e) C/o Pump house, installation of pump | Nalanda | Tourism
13 | 31 |  | BIHAR | C/o New high school building and shifting of existing high school from frontage of Maya Sarovar. | Maya Sarovar | Tourism | 33.11 | 2004-04-01 | [5 empty] | DE/NIT under process. Tender received and under process.
|  |  | BIHAR | Development of Archeological site at Antichak, Bhagalpur. | Bhagalpur | Tourism | 167.41 | [6 empty] | Sectioned awaited PE sent to client by vide No. 23(64)/CE(EZ-II)/944 dt. 30/6/03.
|  |  | BIHAR | Development of scheme for NNM as pilgrimage centre (a) Toursit Circuit | NNM | Culture | 352 | 2004-05-01 | [5 empty] | Site yet to be handed over by client to CPWD arch drg to be issued by Hudco.
| 32 |  | DELHI | Development of Bhagwan Mahavir Vanasthali | Delhi | Culture | 319.7 | 2002-01-01 | - | - | 2004-08-01 | 100.26 | 98 | The work had been stopped by the forest deptt. Of Delhi Govt. and was delayed due to the non availablity of cement in the Central stores. The forest deptt. had objected to the work of making path etc. However the work has now been completed.
|  |  | DELHI | SH: Providing & laying sand stone flooring in path ways | Delhi | Culture |  |  | 2002-07-01 | 2002-11-01 | 2004-02-01 |  | 100 | Work completed
|  |  | DELHI | SH: C/o compound wall with MS grills. | Delhi | Culture |  |  | 2002-06-01 | 2002-10-01 |  |  | 100 | Work completed
|  |  | DELHI | SH: C/o Toilet Block with septic Tank | Delhi | Culture |  |  | 2001-10-01 | 2002-02-01 | 2004-03-01 |  | 100 | Work completed
|  |  | DELHI | SH: C/o Triller | Delhi | Culture |  |  | 2002-08-01 | 2002-09-01 |  |  | 100 | Work completed
|  |  | DELHI | SH: C/o Bridges | Delhi | Culture |  |  | 2002-08-01 | 2002-11-01 | 2004-08-01 |  | 90 | Work in progress.
|  |  | DELHI | SH: P/F paver in parking area. | Delhi | Culture |  |  | 2002-08-01 | 2002-09-01 |  |  | 100 | Work completed
|  |  | DELHI | SH: C/o area around toran dwar | Delhi | Culture |  |  | 2002-10-01 | 2003-01-01 |  |  | 100 | Work completed
|  |  | DELHI | SH: Water supply | Delhi | Culture |  |  | 2004-01-01 | 2004-02-01 | 2004-02-01 |  | 100 | Work completed
|  |  | DELHI | SH: C/o Rain shelter | Delhi | Culture |  |  | 2003-11-01 | 2004-02-01 | 2004-08-01 |  | 100 | Work completed
|  |  | DELHI | SH: Providing deep tube well | Delhi | Culture |  |  |  |  | 2004-04-01 |  | 100 | Work completed
|  |  | DELHI | SH: C/o Seatings | Delhi | Culture |  |  | 2004-01-01 | 2004-03-01 | 2004-08-01 |  | 100 | Work completed
|  |  | DELHI | Survey of Addl. Land | Delhi | Culture
|  |  | DELHI | C/o Cabin for office entry | Delhi | Culture |  |  |  |  | 2004-08-01 |  | 100 | Work completed
|  |  | DELHI | Disposal of Malba | Delhi | Culture |  |  |  |  | 2004-08-01 |  | 100 | Work completed
| 33 | 25 | DELHI | Development of front town at Humayu Town New Delhi. Road work Boundary wall stone flooring | Delhi | Culture | 181.1 | - | - | - | - | 62.49 | 100 | Work completed.
| 34 | 26 | DELHI | C/o Jai Prakash Narain Memorial Park Bahadur Shah Zafar Marg | Delhi | Culture | 197 | 12.7.02 | 2002-08-01 | 2004-08-01 | 2004-04-01 | 178.13 | 100 | Work Completed.
| 35 | 27 | DELHI | Redevelopment of Darshan Complex, New Delhi. | Delhi | Culture | 347 | 7.6.02 | 2002-07-01 | 2003-06-01 | 2004-06-01 | 116.68 | 85 | Funds of Rs. 2.13 crores only received so Far. Work in progress.
| 36 |  | DELHI | Earth filling and horticulture works | Delhi | Culture | 48.17 | - | - | 2002-11-01 | 2004-06-01 | 13.18 | 75 | Work in progress.
| 37 |  | DELHI | Storm water drainage | Delhi | Culture | 19.54 | - | 26.10.02 | 2003-01-01 |  | 11.63 | 100 | Work completed
| 38 |  | DELHI | Laying of water supply grid for horticulture purpose | Delhi | Culture | 6.48 | - | 17.02.03 | 2003-04-01 |  | 4.93 | 100 | Work completed
| 39 |  | DELHI | C/o lagoon water body at Gandhi Darshan | Delhi | Culture | 38.8 | - | 15.3.03 | 2003-06-01 |  | 12.37 | 100 | Work completed
| 40 |  | DELHI | C/o planters for tree | Delhi | Culture | 3.5 | - | 1.05.03 | 2003-06-01 |  | 4.37 | 100 | Work completed
| 41 |  | DELHI | C/o road and parking | Delhi | Culture | 21.14 | - | 8.12.03 | 2004-02-01 | 2004-04-01 | 21.18 | 70 | Work in progress.
| 42 |  | DELHI | C/o compound wall entry structure central platform and pathways | Delhi | Culture | 48.89 | - | 20.12.03 | 2004-03-01 | 2004-05-01 | 47.76 | 40 | Work in progress.
| 43 |  | DELHI | Water proofing treatment of kasturba auditorium and office buildings. | Delhi | Culture | 23.38 | - | - | - | - | - | - | Work will be taken up after receipt of balance funds.
| 44 |  | DELHI | Horticulture works | Delhi | Culture | 40 | - | - | - | - | - | -
14 | 45 | 199 | DELHI | Toilets and parking on rear side of Red Fort | Delhi | Tourism | 49.5 | - | - | - | - | 232.1 | 100 | Work completed
15 | 46 | 207 | DELHI | Installation of tub ewell electrical pump at Red Fort | Delhi | Tourism | 2.54 | - | - | - | - | 19 | 100 | Work completed
16 | 47 | 202 | DELHI | Development of lawn infront of Red Fort. | Delhi | Tourism | 300.34 | - | - | - | - |  | 100 | Work completed
17 | 48 | 200 | DELHI | Illumination of Front side from Lahore Gate to Delhi Gate facing Chandni Chowk in Dlehi | Delhi | Tourism | 34 | - | 15.5.04 | 2004-07-01 | 2004-07-01 | 23.61 | 100 | Work completed
18 | 49 | 201 | DELHI | Illumination of remaining wall on the rear site of Red Fort | Delhi | Tourism | 15.1 | - | - | - | - | 2.68 | 100 | Work completed
19 | 50 | 153 | DELHI | Development of plot vacated by MES in front of Delhi Gate, Red Fort | Delhi | Tourism | 51.36 | - | 2004-01-01 | 2004-05-01 | 2004-05-01 | 10.06 | 20 | Work in progress
| 51 | 3 | DELHI | Development of Bhagwan Mahavir Vanasthali. | Delhi | Culture | 193.22 | 2002-01-01 | 2002-07-01 | 2002-11-01 | - | - | - | Work has been stopped by forest deptt.
| 52 | 4 | DELHI | C/o National Gallery of Modern Art at Jaipur House, New Delhi. | Delhi | Culture | 4945 | 2002-06-01 | 2003-04-01 | 2005-04-01 | 2005-04-01 | 1188 | 30 | Work in progress. Block-1 auditorium slab casting in progress. Stuctural details for 1st blab (+) 160 of Block-III, Slab LVL+3840 of Block -II still awaited from SE(RR), CDO.
| 53 |  | DELHI | Development of lawn infront of Red Fort. ( SH: Improvement of Road with Micro -Surfacing, Grass Pavers, and TOE wall with MS pipe Railing) | Delhi | Culture | 44.88 | 4.9.03 | - | - | - | 33 | 100 | Work Completed.
| 54 |  | DELHI | Development of lawn front of red fort New Delhi | Delhi | Culture | 191.66 | - | - | - | - | 232.1 | 100 | Work Completed
| 55 |  | DELHI | C/o Ticket Booth and Clock room in front of Red Fort | Delhi | Culture | 48.31 | - | - | - | - | 41.69 | 100 | Work Completed
| 56 |  | DELHI | Dismantling of temporary Block No. 28, 29, 30 in ground of Mes near Khas Road, Red Fort | Delhi | Culture | 2.86 | - | - | - | - | 1.93 | 100 | Work Completed
| 57 |  | DELHI | Dismantling of temporary Block No. 28, 29, 30 in ground of Mes near Khas Road, Red Fort | Delhi | Culture | 37.11 | - | - | 30.6.04 | 31.10.04 | 17.24 | 25 | Work of restoration of Ashad Burj yet to be taken up. Renovation can not be taken up due to PIL in sureme court
| 58 |  | DELHI | Redevelopment of Old fort campus at Mathura Road, ND | Delhi | Culture | 15.38 | - | 11.1.04 | 10.3.04 | 20.4.04 | 11.16 | 60 | Work held up due to non-removal of structures by MCD/ASI
| 59 |  | DELHI | Development of lawn front of red fort New Delhi (SH : Providing and fixing signages) | Delhi | Culture | 6.82 | 20.11.03 | - | - | - | - | - | Tenders received in Divn. Office and yet to be awarded.
| 60 |  | DELHI | Renovation of ASI Institute at 24, Tilak Marg, ND | Delhi | Culture | 78 | - | 15.11.03 | 14.2.04 | 30.5.04 | 8 | 40 | Work in progress
| 61 |  | DELHI | Redevelopment of Ferozshah Kotla Monument. | Delhi | Culture | 51.23 | - | - | 30.6.04 | 31.12.04 | 0.38 |  | Sample work yet to be approved.
| 62 |  | DELHI | Redevelopment of Rajghat and its surroundings (a) c/o Toilet block, Kiosks, Etc. Delhi | Delhi | Culture | 37.39 | - | - | - | - | - | - | Work will taken up after receipt of balance funds.
20 | 63 |  | DELHI | Development of Area around Old Fort along Bhairon Marg, Delhi | Delhi | Tourism | 134.75 | - | - | - | - | - | - | Development plan under preparation with SE(HQ)
| 64 |  | DELHI | Development of land behind Express Building as park in continuity with JP Park and Saheed Park, Delhi | Delhi | Culture | 280 | - | - | - | - | - | - | A/A & E/S awaited 125 crores deposited by the client department.
21 | 65 |  | DELHI | C/o Lok Nayak JP Library at Mandir Marg, Delhi | Delhi | Tourism | 282.52 | 2003-12-01 | - | - | - | 9.76 |  | The approval of drawings from NDMC not received. Foundtion stone laid. Leveling of site done.
22 | 66 |  | DELHI | Development of Tourist Complex Opposite Birla Mandir, Mandir marg, ND | Delhi | Tourism | 247.15 | 27.2.04 | 2004-06-01 | 2005-03-01 | 2005-03-01 | - | - | Only park and path work is being taken Tenders due for opening on 17/5/04.
| 67 |  | DELHI | Providing compound lighting and general lighting area under ASI, Red Fort Delhi | Delhi | Culture | 28.59 | - | - | - | - | 9.39 | 50 | Revised estimate has been sent to ASI for approval and balance work like providing poles etc. can be taken up only after receipt of the approval
| 68 |  | DELHI | Development of lawns in between ring road and red Fort, Delhi | Delhi | Culture | 15 | - | - | - | - | 15 | 100 | Work completed.
| 69 |  | DELHI | Providing EI and Fans in barracks at Salimgarh Fort, Delhi | Delhi | Culture | 9.45 | - | - | - | - | 1.13 | 100 | Work completed, however no authorisation received so far.
23 | 70 |  | DELHI | Development of parking and landscaping the area vacated by the territorial Army in Red Fort , Dlehi. | Delhi | Tourism | 103 | 2003-12-01 | - | - | - | - | - | Work not started yet.
| 71 |  | DELHI | Armo Electrical installation for illumination of wall of Red Fort Delhi | Delhi | Culture | 14.77 | - | 1.4.03 | 31.3.04 | 31.3.04 | 14.77 | 100 | Work completed.
| 72 |  | DELHI | C/o National Museum Phase-III, Maulana Azad Road, New Dlehi | Delhi | Culture | 332.3 | - | - | - | - | - | - | Secy, M/o Tourism & Culture, govt. of India, has been requested to expedite the issue of sanction for Rs. 33,22,98,000/- for the above work vide this office letter No. 109(Hindi) dt. 23/4/04.
| 73 |  | DELHI | C/o Barat Gharat Kotla New Delhi | Delhi | Culture | 242.3 | - | - | - | - | - | -
| 74 |  | DELHI | New wing of NGMA at Jaipur House, New Delhi | Delhi | Culture | 4945 | 2002-06-01 | 2003-04-01 | 2005-04-01 | 2005-04-01 | 1168 | 30 | Block-1 auditorium slab castign in progress. Structural detail for first slab + 160 of block-3, slab level + 3840 of block -2 still awaited from SE(RR) CDO
24 | 75 |  | DELHI | Development of front lawn of Humayun Tomb ND | Delhi | Tourism | 181.1 | 2003-03-01 | - | - | - | 64.66 | 100 | Additional work for Development of park as desired by the Hon'ble M/o (T&C) is in progress.
|  |  | DELHI | a) Road Work | Delhi | Tourism | [5 empty] | 28.58 | 100 | Additonal work for development of park as desired by the Hon'ble Minister (T&C) is in progress.
|  |  | DELHI | b) Boundary wall | Delhi | Tourism | [5 empty] | 23.23 | 100
|  |  | DELHI | c) Sand stone footing | Delhi | Tourism | [5 empty] | 12.75 | 100
| 76 |  | DELHI | Development of Swami Dayanad Saraswati Parak, Nehru Nagar, ND | Delhi | Culture | 188.57 | 2004-01-01 | - | 2004-02-01 | 2004-04-01 | - | - | The work is held up due to obstruction made by Jal Board.
| 77 |  | DELHI | Development of Balmiki Park at Kasturba Nagar, ND | Delhi | Culture | 15.46 | 2004-03-01 | - | - | - | - | - | Horticulture work in progress.
| 78 |  | DELHI | C/o NMI Bldg at A-19, Sector-62, Instt Area, Noida | Noida | [8 empty] | Requisition received from Clinet, PE yet to be sent (Senior Arch-II) has been asked to prepare preliminary drawings.
| 79 |  | GUJRAT | Jain Temple, Bhiloda, Gujrat | Bhiloda | Culture | 25.19 | - | - | - | - | - | - | Work consists of common toilet in court yard portion water supply line, sewer line etc. Work complete.
| 80 |  | GUJRAT | Shri Muni Nirbhav Sagar, Jan Kalyan Samiti, Jain Temple, Umata | Umata | Culture | 69.98 | 8.3.02 | 2002-06-01 | 2002-12-01 | - | 55.48 | 100 | Work completed and handed over.
| 81 |  | GUJRAT | Kumbhariaji | Kumbhariaji | Culture | 24.72 | 8.3.02 | 2002-06-01 | 2002-12-01 | - | 22.98 | 100 | Work completed and handed over.
| 82 |  | GUJRAT | Jain Temple Borianes, Distt Surender Nagar | Surender Nagar | Culture | 56.5 | 18.11.02 | 2004-03-01 | 2004-11-01 | 2004-11-01 | - | - | Work consists of developmental work in and around Jain Monument. Tender under process.
| 83 |  | GUJRAT | Jain Temple Sherisha Mehsana. | Mehsana | Culture | 60.4 | 18.11.02 | 2003-06-01 | 2004-01-01 | 2004-04-01 | 43.56 | 99 | Work consists of developmental work in and around Jain Monument. Work since awarded and will be completed June' 2004.
| 84 |  | GUJRAT | Jain Temple at Wankaner | Wankaner | Culture | 39.47 | 18.11.02 | 2004-03-01 | 2004-11-01 | 2004-11-01 | 4.57 | - | Work consists of developmental work in and around Jain Monument. Work since awarded and will be completed in Nov. 04
| 85 |  | GUJRAT | Jain Temple at Taranga Hills (phase-I) | Taranga Hills | Culture | 50 | 18.11.02 | 2003-08-01 | 2004-02-01 | 2004-05-01 | 23.45 | 95 | Work consists of development work in and around Jain Monument. Work nearing completion.
| 86 |  | GUJRAT | Jain Temple at Taranga Hills (Phase-II) | Taranga Hills | Culture | 84 | - | - | - | - | - | - | Drawings awaited from Jain Trust. Approval of Forest Deptt regarding land acquisition to be done by Trust. DE under preparation.
| 87 |  | GUJRAT | Jain Temple at Palitana | Palitana | Culture | 304.33 | 21.11.02 | 2003-11-01 | 2004-11-01 | 2004-11-01 | 34.5 | 15 | Work consists of development work in and around Jain Monument. Work in progress .
| 88 |  | GUJRAT | Jain Tirth, Girnar | Girnar | Culture | 186.45 | 3.12.02 | 2003-12-01 | 2004-12-01 | 2004-12-01 | 6.46 | 10 | Work consists of development work in and around Jain Monument. Work in progress .
| 89 |  | GUJRAT | Jain Tirth, Girnar , Phase -II | Girnar | Culture | 70 | 31.3.03 | 2004-04-01 | 2004-12-01 | 2004-12-01 | - | - | Tender received on 22/3/04 and under scrutiny.
| 90 |  | GUJRAT | Jain Temple Campus, Shankheswara, Mehsana. | Mehsana | Culture | 70 | 10.3.03 | 2004-04-01 | 2004-12-01 | 2004-12-01 | - | - | Tender received on 26/3/04 and under scrutiny.
| 91 |  | GUJRAT | Development of ASI site at Adlaj, Gujrat | Adlaj | Culture | - | - | - | - | - | - | - | Drgs. Submitted to ASI in 3/03. Approval awaited.
| 92 |  | GUJRAT | Development of ASI site Modhera | Modhera | Culture | 88 | 7.6.03 | - | - | - | - | - | Drgs. Submitted to ASI in 3/03. Approval awaited. Drgs. Recd, for wall. & Tenders for the same being called.
25 | 93 | 40 | HARYANA | Development of Kurkshetra (SH: Tapovan Park A (Phase II) | Kurkshetra | Tourism | 70.27 | 2002-11-01 | 2003-04-01 | 2004-02-01 | 2004-02-01 | - | 100 | (A) A sanction of Rs. 70.27 lacs was received on 12.11.2002 for the work. The earth filling of the Tapovan Park-A has been completed. The work for civil and horticulture landscape in the Park is in progress. The civil landscape work is likely to be completed by February 2004. The Horticulture landscaping shall be completed in April 2004. Present progress of work is 95%. (B) A sanction of Rs. 320.00 Lacs was received on 8.3.2002 for the construction of road and development of Tapovan Park. The 4 laning work was completed in December 2002 before the Geeta Jyanti Festival. Inventry handed over. However Taken over notes are yet to be received from EE, PWD (Haryana).
26 | 94 | 39 | HARYANA | Providing lighting arraagement at Brahm Sarovar | Brahm Sarovar | Tourism | 70.26 | - | - | - | - | 70 | 100 | The work costing around Rs. 70.26 lacs was completed before the target date in 2003 i.e. well before the expected time of Solar Eclipse and has been handed over.
27 | 95 | 38 | HARYANA | Renovation of Jyotisar SH: Horticulture & land scaping work | Jyotisar | Tourism | 43.66 | - | - | - | - | - | - | A sanction of Rs. 40.98 + 2.68 lacs was received for the horticulture and the civil landscape works of the Jyotisar. The civil landscape works and the horticulture works have been completed & handed over.
28 | 96 | 37 | HARYANA | Renovation of Jyotisar SH: Civil works | Jyotisar | Tourism | 121.99 | - | - | - | - | - | 100 | A sanction of Rs. 42.17 Lacs was received on 01.07.2002 for construction of paths, horticulture works and illumination of these monuments. All these works have been completed & handed over. (ii) A sanction of Rs. 55.46 lacs was received for construction of boundary wall around Harsh Ka Tilla. The work has been completed for the portion of land handed over to CPWD with a saving of approximately Rs. 20 Lacs. About 75 metre length of boundary wall could not be completed as possession of land has not given to CPWD by ASI. The works of construction of drainage system for Harsh Ka Tilla at a cost of Rs. 15.5 lacs have also been completed & handed over. Civil works at Brahm Sarovar :(iii) A sanction of Rs. 24.34 lacs was received for the horticulture landscaping and providing paths inside this park. The work of providing paths and that of the horticulture landscape was completed and handed over.
29 | 97 | 78 | HARYANA | Providing Roof over view Gallery at Jyotisar | Jyotisar | Tourism | 2.68 | - | - | - | - | - | - | A sanction of Rs. 2.68 lacs was received in 2003-04. Matter discussed with the Architect and CPWD Architect wing is of the view that this will not match with suroundings and hence has not been constructed.
30 | 98 | 14 | HARYANA | Integrated development of Tourism circuit from ADI Badri | Badri Rakhigarhi Kalibanga | Tourism | 228 | - | - | - | - | - | - | A sanction of Rs. 228.00 lacs has been received on 12.11.03 as details under:- (i) C/o Archaeological Complex at ADI Badri (Rs. 72.00 Lacs) (ii) C/o Archaeological Complex at Rakhigarhi (Rs. 52.00 Lacs) (iii) C/o Archaeological Complex at Banawali (Rs. 52.00 Lacs). (iv) C/o Archaeological Complex at Ka Kalibanga (Rs. 52.00 Lacs). Funds allotted to EE Karnal Central Divn. for Rs. 88 Lacs for (i) (ii) (iii) & 26 Lacs has been allotted to EE Bikaner Central Divn. The site are yet to be handed over by ASI. Detail working drg. are also awaited from Chief Arch. Hudco. EE have also met in person being told that Drg. preparation is in progress.
| 99 |  | HARYANA | Jain Temple, Ganaur, Haryana | Ganaur | Culture | 15 | - | 2002-09-01 | 2002-12-01 | 2004-04-01 | - | 100 | Work consists of development work in and around Jain Monument. Work awarded and it was stopped by the Trust, because they want to change the scope of work.
31 | 100 |  | HARYANA | Development of Kurukshetra, Dev of Tapovan Park-A, Civil & Horticulture works, Boudnary wall & Garden lights | Kurukshetra | Tourism | 390.27 | 8.3.02 | 15.5.02 | 14.09.02 | 31.5.04 | 375 | 99 | Garden lighting is in final stage of completion
32 | 101 |  | HARYANA | Development of Kurukshetra, Dev of Tapovan Park-B, Phase-II | Kurukshetra | Tourism | 125.84 | 12.11.03 | - | - | - | - | - | Tender called for earth filling & expected in May 05. on 17/5/04. Balance item will be taken up only after earth filling as site is slushy. Tender rejected and are being recalled.
| 102 |  | HARYANA | C/o IHM at Kurukshetra | Kurukshetra | Culture | 1498 | 8.10.04 | - | - | - | - | - | Boundary wall completed Arch. Drgs. under preparations. Tender rejected & ae being recalled.
| 103 |  | HARYANA | Development of Kurushetra SH; MS grill on sides of Jhama Road, Carpetting of 100 road & hort, work of | Kurushetra | Culture | 42.8 | 31.1.03 | - | - | - | - | - | Sanction not received and not requried as it is not feasible at site to provide grill. Carpetting of road has already been done by state govt.
| 104 |  | HARYANA | Renovation of Sarovar at Rin Mochan & Kapal Mochan at Yamuna Nagar | Yamuna Nagar | Culture | 50.54 | 21.8.03 | 4.12.03 | 3.3.04 | - | 40 | 100 | Civil work completed Compound lighting in progress.
33 | 105 |  | HARYANA | C/o ASI Complex at Adi Badri | Adi Badri | Tourism | 72 | 12.11.03 | - | - | - | - | - | Site not yet handed over by ASI.
| 106 |  | HARYANA | C/o ASI Complex at Thanesar, KKR | Thanesar | Culture | 250 | 12.11.03 | - | - | - | - | - | Site not yet handed over by ASI.
| 107 |  | HARYANA | C/o ASI Complex at Banwal, Hisar | Banwal | Culture | 52 | 12.11.03 | - | - | - | - | - | Site not yet handed over by ASI.
| 108 |  | HARYANA | C/o ASI Complex at Rakhigarhi, Hisar | Rakhigarhi | Culture | 52 | 12.11.03 | - | - | - | - | - | Site not yet handed over by ASI.
| 109 |  | HARYANA | C/o ASI Complex at Sirsa | Sirsa | Culture | 52 | 12.11.03 | - | - | - | - | - | Site not yet handed over by ASI.
| 110 |  | HARYANA | Development of Kurushetra SH; Providing lighting arrangement at Brahm Sarovar (East & West) | Kurukshetra | Culture | 70.26 | 12.11.02 | - | - | 30.06.04 | 60 | 98 | a. Lighting work in ladies ghats completed. b.Lighting arrangement around parikrama & lighting to temple complete. C. High west lighting work complete d. Miscellaneous additional work as demanded in progress likely to be completed by 15th July.
34 | 111 |  | HARYANA | Renovation of Jyotisar (Kurukshetra) SH: Providing of Sub Station, DG Set, Path Lighting int. EI split type AC Units | Kurukshetra | Tourism | 40.96 | 12.11.02 | - | - | 30.06.04 | 34.56 | 95 | a. Substation work completed. B. DG set work completed c. Path lighting work in front side & rear side complete. D. Int. E. I. Work complete e. Split AC unit work complete f. Miscellaneous additional work as demanded in progress.
35 | 112 |  | HARYANA | C/o Archeological Complex at Adi Badri (Distt. Yamuna Nagar) | Adi Badri | Tourism | 72 | 12.11.03 | - | - | - | - | - | Elect work shall be taken up along with civil works.
| 113 |  | HARYANA | C/o Archeological Complex at Thanesar ( Distt. Kurukshetra) | Thanesar | Culture | 2.5 | 12.11.03 | - | - | - | - | - | Elect work shall be taken up along with civil works.
| 114 |  | HARYANA | C/o Archeological Complex at Rakhi( Distt. Hisar) SH: Elect. work | Hisar | Culture | 13.11 | 12.11.03 | - | - | - | - | - | Elect work shall be taken up along with civil works.
| 115 |  | HARYANA | C/o Archeological Complex at Bana wali ( Distt Fatehabad). SH: Elect. work | Fatehabad | Culture | 13.11 | 12.11.03 | - | - | - | - | - | Elect work shall be taken up along with civil works.
| 116 |  | HARYANA | C/o Archeological Complex at Sirsa SH: Elect. work | Sirsa | Culture | 13.11 | 12.11.03 | - | - | - | - | - | Elect work shall be taken up along with civil works.
| 117 |  | HARYANA | C/o Institute of Hotel Management at Kurukshetra. SH: Elect. work | Kurushetra | Culture | 14.98 | 8.1.04 | - | - | - | - | - | Elect work shall be taken up along with civil works.
| 118 |  | HARYANA | Landscaping, and illumination of Harsh Vardhan Park / Harsh Ka Tilla at Kurushetra. SH : Illumination of Shiekh Chilli Tomb and Harsh Vardhan Park. | Kurushetra | Culture | 42.18 | 4.10.02 | 22.9.02 | 21.11.02 | 30.6.04 | 34.4 | 100 | a. Façade lighting and path lighting work complete b. Miscellaneous additional work as demanded in progress.
| 119 |  | HARYANA | Providing submersible pump set for filling of Rin Mochan & Kapal Mochan Pathing tank at Bilas pur (Distt Yamuna Nagar) | Yamuna Nagar | Culture | 3 | 10.3.03 | - | - | 30.6.04 | - | 100 | a. Superersible pump work at Rin Mochan complete. B. Borewell data for Kapal Mochan still awaited from CGW-B Ambala.
| 120 |  | HARYANA | Renovation of Rin Mochan at Bilas pur (Distt Yamuna Nagar) SH: Providing lighting arrangement. | Yamuna Nagar | Culture | 50.54 | 21.8.03 | 2004-08-01 | - | 30.6.04 | - | - | Work awarded likely to be completed by 31/7/04.
| 121 |  | HARYANA | Development of Kurukshetra as part of Bharat Darshan Theme park in commemoration of 50th anniversary of Indian Republic (SH: Providing lighting in Tapovan Park -A) | Kurukshetra | Culture | 3.2 | 8.3.02 | - | - | 30.6.04 | 3.78 | 60 | Material procured. Cables laying completed. Poles installation work in progress.
| 122 |  | HARYANA | Development of Kurkshetra (SH: Tokoval Park PH-II) | Kurukshetra | Culture | 126 | - | - | - | - | - | - | A/A &E/S awaited.
| 123 |  | HARYANA | Landscape of Saraswati Tirath at Pedowa. | Pedowa | Culture | 134.66 | - | - | - | - | - | - | A/A &E/S awaited.
| 124 |  | BIHAR | Development work Jain Temple Shikherji Jharkhand | Shikherji | Culture | 25 | 2002-12-01 | 2003-09-01 | 2004-06-01 | 2004-06-01 | 15.67 | 100 | Work completed.
36 | 125 | 77 | J&K | C/o Mahabodhi International Meditation Centre, at Leh SH: Meditation hall. | Leh | Tourism | 49.64 | 20.11.02 | 24.5.03 | 23.11.03 | 2004-05-01 | 40.53 | 100 | Civil work completed in May 04. Electic work in progress.
37 | 126 | 78 | J&K | Lighting of Leh Palace and adjoining protected bldgs. SH: Pdg. Flood lights, laying of cable and feeder pillars. | Leh | Tourism | 18.74 | 6.8.02 | 2003-11-01 | 2004-03-01 | 2004-03-01 | 18 | 100 | Work completed
| 127 |  | J&K | Lighting of Leh Palace and adjoining protected bldgs. SH: 40KVA DG Set | Leh | Culture | 17 | 6.8.02 | 2003-03-01 | 2003-07-01 | 2003-07-01 | 17 | 100 | Work completed
| 128 | 7 | J&K | C/o Boys Hostel for CIBS. | Leh | Culture | 259.59 | 18.3.02 | 2003-06-01 | 2004-09-01 | 2004-09-04 | 45.84 | 52 | Progress slow due to Ladakhi pattern in RCC Plastering.
| 129 | 8 | J&K | C/o Girls Hostels for CIBS. | Leh | Culture | 259.59 | 18.3.02 | 2003-08-01 | 2004-09-01 | 2004-09-04 | 35.38 | 50 | Progress slow due to Ladakhi pattern in RCC Plastering.
| 130 | 9 | J&K | C/o Guest House for CIBS at Leh. | Leh | Culture | 28.28 | 2002-05-01 | 2003-10-01 | 2004-08-01 | 2005-07-01 | 4.29 | 8 | Progress slow due to Ladakhi pattern in RCC Plastering.
| 131 | 10 | J&K | C/o Library Bldg. | Leh | Culture | 217.69 | 11.7.02 | 2002-11-01 | 2003-05-01 | 2004-10-01 | 158.67 | 70 | work in progress.
|  | (a) | J&K | Bldg. works I/c W/S & S/I. Leh | Leh | Culture | - | - | - | - | - | - | - | Work has been suspended due to severe winter.
|  | (b) | J&K | Development and Bulk services. Leh | Leh | Culture | - | - | - | - | - | - | - | Work being done in developed campus.
|  | (a) | J&K | Bldg. works I/c W/S & S/I. Leh | Leh | Culture | - | - | - | - | - | - | - | Work suspended due to severe winter.
|  | (b) | J&K | Development and Bulk services. Leh | Leh | Culture | - | - | - | - | - | - | - | Work being done in developed campus.
|  | (a) | J&K | Bldg. works I/c W/S & S/I. Leh | Leh | Culture | - | - | - | - | - | - | - | Work suspended due to severe winter.
|  | (b) | J&K | Development and Bulk services.Leh | Leh | Culture | - | - | - | - | - | - | - | Work suspended due to severe winter.
| 132 |  | J&K | C/o Institute bldg. For Hotel mangemetn at Rajbagh, Srinagar | Srinagar | Culture | 714.52 | 2003-12-01 | 2004-03-01 | 2005-09-01 | 2005-09-01 | nil | 13 | Work is in progress.
| 133 |  | J&K | C/o Auditorium Block at CIBS at Leh | Leh | Culture | 214.53 | 2.5.02 | - | - | - | - | - | DE under process in the o/o CE(NZ-I)
| 134 |  | J&K | C/o Residential qurts. For CIBS at Leh | Leh | Culture | 3.5.17 | 2.5.02 | - | - | - | - | - | Drwaing being modified by SA(NZ-I)
| 135 |  | J&K | Site Development of CIBS at Leh | Leh | Culture | 342.69 | 2.5.02 | - | - | - | - | - | Tenders for tubewell invited. Planning for site Development of the campus is being done.
| 136 | 18 | KARNATAKA | Renovation of Manickyavelu Mansion for NGMA at Palace Road, Bangalore. (a) Civil. (b) Internal EI. | Bangalore | Culture | 777.71 | 2001-12-01 | 2003-03-01 | 2004-07-04 | 2004-08-01 | 294.47 | 90 | Finishing and toilet under progress. Wooden flooring in progress. DE under process for Mansion & Auditorium. Elect. Work in progress with civil work. DE under process for Development work . Tech bid opened & under scrutiny for fire alarming. PA system, pumpset, secutiny lighting DE under preparation. work awarded for substation, Airconditioning & DG set.
| 137 | 81 | KARNATAKA | Interpretation centre cum shopping node, heritage development works at Hampi | Hampi | Culture | 495 | 2003-03-01 | 2003-05-01 | 2004-05-01 | 2004-08-01 | 87.66 | 25 | Site was handedover to CPWD on 13/5/03. There was encroachment problem in the site, which was sorted ourt by Tourism Deptt., on 24/4/04 and demarcation of the boundary was done accordingly. Based on the discussions held with UNESCO team and other concerned authorities, Consultant, Chief (D&D), Hudco requested CPWD to hold up the construction for revising drawing. Revised draings received on 29/1/03. The revised drawing issued was not feasible to be adopted at site. The matter was further discussed ad the consultant informed over phone during 2nd week of may 2004 to proceed with work.
|  |  | KARNATAKA | Interpretation centre cum shopping node, heritage development works at Hampi | Hampi | Culture | [7 empty] | The consultant Chief (D&D) HUDCO, again intimated CPWD during 2nd week of 6/04 that UNESCO authorities has taken objection regarding RCC structures being constructed and hence the work should be hold up till further decision is given. The decision is still awaited. There is delay on the part of the contractor also. The interruptions as explained above causing further delay by the contractor.
|  |  | KARNATAKA | (I) SH: Interpretation cum shopping node | Hampi | Culture | - | - | 2003-05-01 | 2004-05-01 | 2005-03-01 | 12.52 | 20 | a) Western side- Columns of 4 blocks have been reached to slab level. Rest 1 block plinth beam have been casted, columns are being raised. The 39 Nos. oranamental columns, (Corridor columns) footings have been laid. b) Eastern side- All 5 blocks columns have reached upto slab level. The latest modified final Arch. drgs were received only on 29/01/2004. The columns sizes have been modified and increased.
|  |  | KARNATAKA | (ii) SH: Development works | Hampi | Culture | - | - | 2003-05-01 | 2004-01-01 | 2004-07-01 | - | 18 | UG sump, excavation of black cotton soil and filling with good earth are in progress. The modified LOP to be recd from HUDCO.
|  |  | KARNATAKA | (iii) Diversion of Nallah | Hampi | Culture | 8.65 | 2004-01-01 | 2004-01-01 | 2004-08-01 | 2004-08-01 | 11.1 | - | The main Nallah belongs to the Irrigation Deptt., of Govt. of Karnataka. The Irrigation deptt has given an estimate of Rs. 8.65 lakhs which was late revised to Rs. 11.10 lakhs. Accordinlgy, the amount of Rs. 11.10 lakhs has been deposited with the Irrigation deptt. out of the estimated length of 340 m, about 190 m work has been carried out. it is expected the remaining work will be completed by the end of Aug-04.
| 138 |  | KARNATAKA | Interpretation centre cum shopping node, heritage development works at Hampi SH: Pavements, Roads, Open Air Theatres | Hampi | Culture | 241 | - | - | - | - | - | - | PE for Rs. 2,41,47,000/- was sent on 7/11/03 by CE (SZ-3) A/A & E/S awaited.
| 139 |  | KARNATAKA | Providing floodlighting at Haysala Temple at Halebidu | Halebidu | Culture | 64.03 | 2004-03-01 | 2004-06-01 | 2004-09-01 | - | - | - | The work will be completed by the stipulated time.
| 140 |  | KARNATAKA | Jain Temple Arasikeri Karnataka | Arasikeri | Culture | 6.36 | - | - | - | - | - | 100 | Work consists of C/o Boundary wall with barbed wire fencing & removal of surplus earth etc. Work since completed.
| 141 |  | KARNATAKA | Jain Temple Hadvalli, Karnataka | Hadvalli | Culture | 24.7 | - | - | - | 2004-04-01 | - | 90 | Work consists of developmental work in and around Jain Monument. Work stopped by the contractor and notice issued to the contractor accoridngly work will be completed by Apr-04.
| 142 |  | KARNATAKA | Jain Temple Sondha, Karnataka | Sondha | Culture | 14.96 | - | - | - | 2004-04-01 | - | 80 | Work consists of development work and in around Jain Monument. The present progress of work will be 80% & will be completed April -04
| 143 |  | KARNATAKA | Old Temple at Biligi near Siddapur. | Siddapur | Culture | 11.21 | 2002-11-01 | 2003-03-01 | 2003-08-01 | - | 0.03 | - | ASI not given clearance. Proposal is sent to the Ministry of shifting the work to Sirsi.
| 144 | 17 | KARNATAKA | C/o Office bldg. & staff qrs. For ASI at Dharwar | Dharwar | Culture | 317.35 | 2001-03-01 | 2002-02-01 | 2003-05-01 | 2004-10-01 | 146.98 | 90 | 2nd floor plastering almost completed flooring and tilet works in progress. Qtrs final finishing in progress.
| 145 |  | KARNATAKA | SH: Bldg. Portion Office bldg. and staff qtrs. | Dharwar | Culture | 37.35 | 2001-03-01 | 2002-02-01 | 2003-02-01 | 2004-06-01 | 90.45 | 77 | Qtrs. - Fixing of Door shutter sanitary works are in process.
| 146 |  | KARNATAKA | Renovation of old temple at Banavasi (Near Sirisi) | Banavasi | Culture | 12.44 | - | - | - | 2004-03-01 | - | 90 | Work consists of Development work in and around Jain Monument. Work awarded and shall be completed by 31.3.04.
| 147 |  | KARNATAKA | C/o Facilitation Centre cum interpretation Centre for Chandraprabha basti at Hadivali | Haduvalli | Culture | 27.89 | 2002-08-01 | 2002-12-01 | 2003-06-01 | 2004-11-01 | 4.22 | 10 | Foundation completed. Work rescinded. Tenders for balance work awarded on 7/2004 with stipulated period of 120 days for completion.
| 148 |  | KARNATAKA | C/o Covered parking area toilet and Dev. Work at Veera Mahasati Basti, Haduvalli | Haduvalli | Culture | 27.89 | 2002-11-01 | 2003-03-01 | 2003-08-01 | 2004-09-01 | 14.08 | 92 | painting work in progress.
| 149 |  | KARNATAKA | C/o Covered parking area toilet and Dev. Work at Chandragiri Basti, Haduvalli | Haduvalli | Culture | 27.89 | 2002-11-01 | 2003-03-01 | 2003-08-01 | 2004-10-01 | 19.81 | 92 | painting work in progress.
| 150 |  | KARNATAKA | C/o Covered parking area, toilet, cloak cum compound wall at Srikshetra. | Srikshetra | Culture | 15 | 2003-02-01 | 2003-06-01 | 2003-10-01 | 2004-12-01 | 0.04 | 1 | Site since handed over by client. Work just started.
| 151 |  | KARNATAKA | C/o Facilitation Centre and development works at Gauru Basti temple at Moodabidri, Mangalore. | Moodabidri | Culture | 29.79 | 2002-09-01 | 2003-01-01 | 2003-05-01 | 2004-09-01 | 8.45 | 99 | Main work completed. Othe work in progress.
| 152 |  | KARNATAKA | Shed, Clock room toilets and Development works of Neminath Temple at Biligi. | Biligi | Culture | 11.21 | 2002-11-01 | 2003-05-01 | 2003-08-01 |  |  |  | ASI has not yet given clearance & approval for taking this work to Sirai.
| 153 |  | KARNATAKA | C/o Facilitation Centre and development works at Adinath Temple, Raibag, Belgaum, Distt. | Raibag | Culture | 24.5 | 2002-06-01 | 2002-09-01 | 2003-02-01 | 2004-09-01 | 17.05 | 95 | Development work are in progress.
| 154 |  | KARNATAKA | Shed, Clock room toilets and Development works of Neminath Temple at Sonday, Sirsi Taluk | Sonday | Culture | 14.96 | 2002-09-01 | 2003-01-01 | 2003-05-01 | 2004-09-01 | 9.76 | 95 | painting work in progress. Delay due to rain.
| 155 |  | KARNATAKA | Shed, Clock room toilets and Development works of Neminath Temple in Banavasi | Banavasi | Culture | 23.65 | 2002-11-01 | 2003-03-01 | 2003-08-01 | 2004-10-01 | 7.78 | 80 | Finishing work are in progress.
| 156 |  | KARNATAKA | Providing special illumination to Vittala temple, Hampi | Hampi | Culture | 39.22 | 2002-02-01 | - | - | - | 39.92 | 100 | Work completed.
| 157 |  | KARNATAKA | Providing special illumination to Bazaar area, mandaps and compound lighting of Vittala temple, Hampi | Hampi | Culture | 57.03 | 2002-07-01 | - | - | 2004-07-01 | 18.37 | 100 | Work completed.
| 158 |  | KARNATAKA | Providing fiber optic lighting to Virupaksha Temple at Hampi | Hampi | Culture | 68.42 | 2002-11-01 | - | - | 2004-07-01 | 43.49 | 96 | Fiber lighting work completed for other areas in progress.
| 159 |  | KARNATAKA | Providing flood lighting to Fort, at Chitradurga | Chitradurga | Culture | 29.87 | 2003-03-01 | - | - | 2004-05-01 | 29.87 | 100 | Work almost completed.
| 160 |  | KARNATAKA | C/o interpretation Centre cum Noding Centre at Hampi | Hampi | Culture | 48.87 | 2003-01-01 | - | - | 2004-12-01 | 10.29 | 5 | Work just started.
| 161 |  | KARNATAKA | Hogund Basti | - | Culture | 3.14 | - | - | - | - | - | - | Work consists of development work in and around Jain Monument. Work just awarded..
| 162 |  | KARNATAKA | Shree Kshetra, Kambodhalli | Kambodhalli | Culture | 15 | - | - | - | - | - | - | Work consists of developmental work in and around Jain Monument. Work could not be started due to non availability of site.
| 163 | 28 | KARNATAKA | C/o Piligrim amentiy centre at Kullanda Pathonsthti Distt. Kulanda | Kulanda | Culture | 112.74 | 2002-10-01 | 2001-09-01 | 2002-02-01 | - | 126 | 100 | Work completed.
| 164 | 29 | KARNATAKA | C/o Tourist Complex at Thanmukkam Alpppazha Dist. PH I, II, III. Thanner mukkam | Alpppazha | Culture | 149.15 | 2001-11-01 | 2003-03-01 | 2003-09-01 | 2004-06-01 | 139.55 | 92 | Ph-I completed. Ph-II - fixing door and window shutters in progress. Ph-III- Flooring in progress.
| 165 | 30 | KARNATAKA | C/o Cottage for Punmudi Civil works Punmudi | Punmudi | Culture | 116.63 | 2000-10-01 | 2003-09-01 | 2004-03-01 | 2004-07-01 | 30.93 | 80 | MOK unit completed. Ty-I - IV superstructure in progress.
| 166 |  | KARNATAKA | C/o Yatri Niwas at Kumily, Iddukki Distt. | Kumily | Culture | 123.8 | 1999-10-01 | - | - | - | - | - | Land not yet allotted by State Govt.
| 167 |  | KARNATAKA | C/o Yatri way side amenities at Manmor, Idukki Dt. | Manmor | Culture | 112.64 | 2000-06-01 | - | - | - | - | - | Land is to be identified.
| 168 |  | KARNATAKA | C/o Executive Devl. Centre for IHMCT at Banglore | Bangalore | Culture | 395 | Apr-02 | 2003-05-01 | Sept-04 | Sept-04 | 125.08 | 60 | Work in progress.
| 169 |  | KARNATAKA | C/o Executive Devl. Centre for IHMCT at Banglore | Bangalore | Culture | 280 | Apr-02 | -- | -- | -- | -- | --
|  |  | KARNATAKA | a) Main Building | Bangalore | Culture | -- | -- | 2003-05-01 | Sept-04 | Sept-04 | 0 | 60 | RCC completed, Finishing under progress.
|  |  | KARNATAKA | b) Development works civil | Bangalore | Culture | -- | -- | 2002-09-01 | Sept-04 | Sept-04 | 7.07 | 30 | Roads, paths, drains and horticulture are pending.
|  |  | KARNATAKA | c) Development works Elect. | Bangalore | Culture | -- | -- | -- | -- | -- | -- | -- | Applied to BES Com. PQc Works completed during 10/03. Conduit laid in slab.
| 170 |  | KARNATAKA | C/o Girls Hostels for IHM at Chandra Layout Bangalore | Bangalore | Culture | 214.83 | May -04 | Jan-04 | Jan-05 | Jan-05 | 45 | 0.5 | Foundation work in progress.
| 171 |  | KARNATAKA | C/o bldg. For Epigrapty ASI Mysore. | Mysore | Culture | 587 | 2003-11-01 | 2004-06-01 | 2005-11-01 | 2005-11-01 | 11.54 | 1 | Earth work escavation in foundation completed.
| 172 |  | KARNATAKA | C/o 38 Nos. Residential qtrs for ASI Mysore | Mysore | Culture | 253.38 | 1998-12-01 | - | - | - | - | - | A/A &E/S awaited.
| 173 |  | KARNATAKA | C/o Yatri Niwas at Bijapur | Bijapur | Culture | 58 | 1996-07-01 |  | 2004-05-01 |  | 68 | 100 | Work completed and handed over.
| 174 |  | KARNATAKA | C/o Yatri Niwas Dharwad | Dharwad | Culture | 89.21 | 1997-11-01 |  | 2004-05-01 |  | 90.12 | 100 | Work completed and handed over.
| 175 |  | KARNATAKA | C/o Yatri Niwas Soundatti | Sounadatti | Culture | 33.61 | 1996-11-01 |  | 2004-05-01 |  | 42 | 100 | Work completed and handed over.
| 176 |  | KARNATAKA | C/o Minor Node at Kamalapur Hampi | Hampi | Culture | 96.46 | 2004-01-01 | [5 empty] | Copy of rough cost estimate and the preliminary drgs for the works recd from Mr. R. K. Safaya, Chief (D&D), HUDCO, only on 12/4/04 Site not ye handed over. No action could be initiated by CPWD for starting the work as the site is not yet handed over by the Client.
| 177 |  | KARNATAKA | C/o Minor Node at Anegundi, Hampi | Hampi | Culture | 64.15 | 2000-03-01 | [5 empty] | Land yet to be taken over and handed over to CPWD. Approved estimate awiated from HUDCO. DE under preparation.
| 178 |  | KARNATAKA | Minor stoppage point at Anegundi, Hampi | Hampi | Culture | 68.9 | 2000-03-01 | [5 empty] | Land yet to be taken over and handed over to CPWD.
| 179 |  | KARNATAKA | Upgradation of Sanapur Guest House Hampi | Hampi | Culture | 30.71 | 2000-01-01 | [5 empty] | Land yet to be taken over and handed over to CPWD. Approved estimate awiated from HUDCO. DE under preparation.
| 180 |  | KARNATAKA | Enviornment improvement of Pampasarovar Hampi | Hampi | Culture | 46.79 | 2000-02-01 | [5 empty] | Land yet to be taken over and handed over to CPWD. Approved estimate & Drgs recently received from HUDCO. DE?NIT under preparation.
| 181 |  | KARNATAKA | Fencing to Prasanna Narasimha Temple at Krishnapura Hampi | Hampi | Culture | 12.5 | 2000-01-01 | [5 empty] | Tender received and under scrutiny in Divn. Office. Suptd. Archealogist requested vide his letter dt. 9/8/2004 to keep the work in progress.
| 182 |  | KARNATAKA | Fencing to Lakshmi Narayana Temple Sindaghatta, Mandya | Sindaghatta | Culture | 17.01 | 2004-03-01 | [5 empty] | Tender received on 7/04 and under scrutiny.
| 183 |  | KARNATAKA | C/o 4 nos. Ty-I qtrs and Devl works of ASI at Hampi | Hampi | Culture | 11.09 | 2004-03-01 | [5 empty] | Detailed arch drgs awaited for preparation of DE&NIT.
| 184 |  | KARNATAKA | C/o 28 Nos. qtrs for ASI at AIHOLE (Baghalkhot Distt) | Aihole | Culture | 194.64 | [6 empty] | PE already sent and sanctions are awaited. However the requiremetns will be reviewed before sending the RE of 2004-05 in Sept -04. Revised LOP sent to Superintending Archalogist. Dharward by SA vide dt. 11/5/04 for approval.
| 185 |  | KARNATAKA | C/o Museum Bldg. For ASI Halebeedu | Halebeedu | Culture | 100.01 | [6 empty] | PE already sent and sanctions are awaited. However the requiremetns will be reviewed before sending the RE of 2004-05 in Sept -04
| 186 |  | KARNATAKA | C/o Museum Bldg. For ASI Srirangapattana | Srirangapattana | Culture | [7 empty] | PE to be sent.
| 187 |  | KARNATAKA | Improvements to ASI Sultan Battery Fort | Mangalore | Culture | 210 | [6 empty] | PE already sent and sanctions are awaited. However the requiremetns will be reviewed before sending the RE of 2004-05 in Sept -04
| 188 |  | KARNATAKA | Improvement to ASI, Manasthampa at Kotekeri Batsti | Mangalore | Culture | 100 | [6 empty] | PE already sent and sanctions are awaited. However the requiremetns will be reviewed before sending the RE of 2004-05 in Sept -04
| 189 |  | KARNATAKA | Boundary protection wall cum earth retaining wall at Chitradurga fort, ASI | Chitradurga | Culture | 140.67 | [6 empty] | PE already sent and sanctions are awaited. However the requiremetns will be reviewed before sending the RE of 2004-05 in Sept -04
| 190 |  | KARNATAKA | C/o officer bldg for RCL at Mysore | Mysore | Culture | [7 empty] | Work is already completed. Horticultre work is in progress.
| 191 |  | KARNATAKA | Youth Hostel | Karwar | Culture | 46.15 | 1996-12-01 | 1999-05-01 | 2000-09-01 |  | 20.25 | 30 | Work stopped because of land slide.
| 192 | 91 | KERALA | Pay and use toilet at Kumarkom | Kumarkom | Culture | 16 | - | 2003-03-01 | - | - | - | - | As per the meeting with Secretary, Tourism on 15.12.03, the Kerala Tourism Development Corporation, land will be utilised. The work has been since awarded.
| 193 | 90 | KERALA | C/o Boat Jetty at Ernakulam | Ernakulam | Culture | 159.92 | 2003-06-01 | 2004-03-01 | - | - | - | - | The DE has been framed but the provision in the PE is very much less. Hence revised PE is keeping submitted as per the site requirement. Tenders for main TCHY shall be called after pile foundation is in advanced stage. Work awarded. Can be taken up after jetty is vacated by KSWTC. DE under preparation for pile foundation.
| 194 |  | KERALA | Development of walkway alongwith the back water shore, Cochin Phase-II | Chochin | Culture | 114 | 2002-10-01 | 2003-12-01 | 2004-09-01 | 2004-10-01 | 61.34 | 85 | Delay due to nonvacation of jetty by KWTC Pre-cast pile casting in progress. Tender for pile accepted.
| 195 |  | KERALA | Facilitation Centre at Fort Cochin | Chochin | Culture | 199.44 | 2003-06-01 | 2004-08-01 | 2005-08-01 | 2005-08-01 | 21.63 |  | Work since awarded.
| 196 |  | KERALA | Paving of open area at Sooryakanthi, Kanakakunnu Palace, Trivandrum | Trivandrum | Culture | 49.87 | 2002-10-01 | 2003-09-01 | 2004-03-01 | 2004-04-01 | 32.46 | 95 | Work nearing completion
| 197 |  | KERALA | C/o Tourist Resort at Ponmudi | Ponmudi | Culture | 116.63 | 1999-03-01 | 2003-09-01 | 2004-03-01 | 2004-06-01 | 21.29 | 56 | Mock unit completed. Ty-I, II, III & IV in progress.
| 198 |  | KERALA | C/o Wayside amenity at Punalur | Punalur | Culture | 84.13 | 2002-10-01 | 2003-10-01 | 2004-04-01 | 2004-11-01 | 33.52 | 65 | Toilet block stucture is completed. Finishing in progress, centering & shuttering for roof for suit in progress. Additional details reg. kitchen & flooring awaited from Arch. Due to rain the progress could not be achieved. Elect work in progress.
| 199 |  | KERALA | C/o Yatri Niwas at Varkala | Varkala | Culture | 26.37 | 2000-10-01 | -- | -- | -- | 7.99 | 100 | Work completed
| 200 |  | KERALA | C/o Tourism Reception Centre at Thekkady | Thekkady | Culture | 26.62 | 2000-01-01 | -- | -- | -- | 8.64 | 100 | Work completed
| 201 |  | KERALA | C/o Piligrim amentiy centre at Erumeli | Erumeli | Culture | 115.37 | 1999-10-01 | -- | -- | -- | 177.52 | 100 | Work completed
| 202 |  | KERALA | C/o Boat terminal at Nehru Centenary Pavillion. Punnamada at Alleppey a)SH:- Pavillion | Alleppey | Culture | 55.3 | 1998-10-01 | 2003-03-01 | 2003-10-01 | 2004-07-01 | 44.19 | 100 | Work completed
| 203 |  | KERALA | C/o Boat terminal at Nehru Centenary Pavillion. Punnamada at Alleppey b)SH:- Boat terminal | Alleppey | Culture | 43.87 | 1999-11-01 | -- | -- | -- | -- | -- | Tender under scrutiny.
| 204 |  | KERALA | C/o Watersideamenity at Thannermukkom a) Elect. Work | Thannermukkom | Culture | 149.18 | 2001-10-01 | 2002-10-01 | 2003-06-01 | 2004-06-04 | 80.99 | 90 | Flooring work in progress.
| 205 |  | KERALA | C/o Pay & Use toilet at Kollam | Kollam | Culture | 15.98 | 2001-11-01 | -- | -- | -- | 0.57 |  | Work awarded. Approval of Plan awaited from Kollam Municipality.
| 206 |  | KERALA | C/o Conference hall for Tourism deptt. at Changanacherry | Changanacherry | Culture | 15.98 | 2002-10-01 | -- | -- | -- | 7.88 | 100 | Work completed.
| 207 |  | KERALA | C/o Watersideamenity at Pallathuruthi | Pallathuruthi | Culture | 80.72 | 2001-01-01 | 2003-10-01 | 2004-08-01 | 2004-11-01 | 28.4 | 30 | Column being raised above plinth level.
| 208 |  | KERALA | C/o waterside amenity at Nedumudy | Nedumudy | Culture | 69.84 | 2000-10-01 | -- | -- | -- | -- | -- | Tender under scrutiny.
| 209 |  | KERALA | C/o back waterside amenity at Vattakayal, Alleppey | Vattakayal | Culture | 74.42 | -- | -- | -- | -- | -- | -- | Tender under scrutiny.
| 210 |  | KERALA | C/o Yatri Niwas at Munnar | Mannar | Culture | 112.04 | 2000-03-01 | -- | -- | -- | -- | -- | Architectural drgs. Awaited. Site yet to be handed over.
| 211 |  | KERALA | C/o Tourist Complex at Kudarathode | Kudarathode | Culture | 73.11 | 2003-02-01 | 2004-03-01 | 2004-10-01 | 2004-12-01 | 14.26 | 60 | Basement brick work completed. Filling in progress.
| 212 |  | KERALA | C/o Pay & Use toilet at Kumarakam | Kumarakam | Culture | 15.95 | -- | 2004-02-01 | 2004-06-01 | 2004-11-01 | 3.35 | 20 | Superstructure in progress.
| 213 |  | KERALA | C/o boat terminal at Puthanangadi Thanneermukkom | Thanneermukkom | Culture | 71.77 | -- | 2004-04-01 | 2004-10-01 | 2004-12-01 | 5.36 | 6 | Pile work completed. Pile cap casting pending due to labour dispute.
| 214 |  | KERALA | C/o Yatri Niwas at Vagamon | Vagamon | Culture | 44 | 2000-07-01 | -- | -- | -- | -- | -- | Work completed.
| 215 |  | KERALA | C/o Water sports complex at Ashtamudi Lake, Kollam | Kollam | Culture | 45 | 1999-07-01 | -- | -- | -- | -- | -- | Work awarded.
| 216 |  | KERALA | C/o boat jetty and tourist amenity centre at Fort Cochin | Cochin | Culture | 65.32 |  | -- | -- | -- | 63.52 | 100 | Work completed.
| 217 |  | KERALA | Area Development Corporation Vicinity and Food Craft at Fort Kochi | Kochi | Culture | 49.42 | 2000-02-01 | -- | -- | -- | 53.74 | 100 | Work completed.
| 218 |  | KERALA | Area improvement parade ground Baston Bunglow at Fort Kochi | Kochi | Culture | 99 | 2000-05-01 | -- | -- | -- | 84.58 | 100 | Work completed.
| 219 |  | KERALA | Beautification of Beachside walkway at Fort Kochi | Kochi | Culture | 33 | 2000-12-01 | 2002-08-01 | 2002-12-01 | -- | 18.34 | 100 | Frist phase completed.
| 220 |  | KERALA | Lighting of Fort Kochi Heritage Zone at Fort Kochi | Kochi | Culture | 1 | -- | -- | -- | 2004-07-01 | 3.02 | 80 | 40 Lamp posts errected. Balance retendered and work awarded.
| 221 |  | KERALA | C/o Toilet block, 2 units of Food courts and area Development in parking portion in front of St. Francis Church and parade ground for heritage zone. | Kochi | Culture | 26.96 | 2002-10-01 | 2003-03-01 | 2004-06-01 | -- | 17 | 100 | Work completed.
| 222 |  | KERALA | Area improvement - Jewish Synagogue and its environs in Mattancherry | Mattancherry | Culture | 42 | 2002-05-01 | -- | -- | -- | -- |  | Drainage work taken up.
| 223 |  | KERALA | C/o Pay & use toilet at Cochin | Chochin | Culture | 15.95 | 2001-11-01 | -- | -- | -- | 10.99 | 100 | Work completed.
| 224 |  | KERALA | C/o pilgrim facilitation centre at Vallarpadam. | Vallarpadam | Culture | 9.92 | 2002-10-01 | -- | -- | -- | 9.92 | 100 | Work completed.
| 225 |  | KERALA | C/o Yatri Niwas at Kochi | Kochi | Culture | 89.5 | 2002-12-01 | -- | -- | -- | -- | 100 | Work completed.
| 226 |  | KERALA | Development of Boat jetty at kochi back water SH: C/o new boat jetty complex in Kochi Back water near Subhash Park & KSRTC Bus Stand | Kochi | Culture | 60.77 | -- | -- | -- | -- | -- | -- | Work awarded. Can be taken up after jetty is vacated by KSWTC.
| 227 |  | KERALA | C/o 22 nos. Addl. Food courts at Fort Kochi | Kochi | Culture | 345 | 2003-10-01 | 2004-03-01 | 2004-08-01 | 2004-08-01 | 17 | 30 | Work in progress
| 228 |  | KERALA | C/o Tourist Complex at Kalady | Kalady | Culture | 145.4 | 1998-06-01 | -- | -- | 2003-02-01 | 131.52 | 100 | Work completed
| 229 |  | KERALA | C/o Yatri Niwas at Thirunelly | Thriunelly | Culture | 95.85 | 1999-03-01 |  |  |  | 13.33 | 100 | Work completed
| 230 |  | KERALA | C/o Yatri Niwas at Nelliyampathy SH: Road work. | Nelliyampathy | Culture | 45 | 1998-08-01 | -- | -- | -- | 3.43 | -- | Work is to be restarted. Approach road without any encumberance is to be handed over.
| 231 |  | KERALA | C/o Yatri Niwas at Nelliyampathy SH: Providing barbed wire fencing around site. | Nelliyampathy | Culture | 6.68 | 2000-01-01 | -- | -- | -- | 0.01 | -- | Work is to be restarted. Approach road without any encumberance is to be handed over.
| 232 |  | KERALA | C/o Yatri Niwas at Mannarkad | Mannarkad | Culture | 97.16 | 2000-02-01 | -- | -- | -- | 92.09 | 100 | Work completed
| 233 |  | KERALA | C/o Pay & use toilet at KSRTC Bus Station at Guruvayoor | Guruvayoor | Culture | 15.95 | 2001-11-01 | -- | -- | -- | 10.22 | 100 | Work completed. Water supply, Electrical connection, door No. etc. to be obtained.
| 234 |  | KERALA | C/o Pay & use toilet at KSRTC Bus Station at Trichur | Trichur | Culture | 15.95 | 2001-11-01 | -- | -- | -- | 12.03 | 100 | Work completed. Water supply, Electrical connection, door No. etc. to be obtained.
| 235 |  | KERALA | C/o Tourist Lodge C Block at Guruvayoor, Trichur Dt. | Trichur | Culture | 161.69 | [6 empty] | PE submitted.
| 236 | 111 | MADHYA PRADESH | Chanderi as a destination | Chanderi | Culture | 111 | 2003-03-01 | - | - | - | - | - | The sanction has been revised vide M/o T&C, dett of Tourism letter No-5-PSW/50/2002-Pt dt. 24/2/04. CPWD is left with S.No.2, 4 (b)5,6 &7. For Item 2&6 proper estimate are under preparation & Likley to be submitted shortly. Meanwhile S.No. 4(b) 5&7. Arch. planning is going on. A detail report submitted to Deptt. of Tourism No. 2020 dt.20.11.03. The sanciton has been revised vide M/o T&C, Deptt of Tourism letter No.5-PSW/50/2002-Pt dt. 24/2/2004.
|  | (a) | MADHYA PRADESH | SH: Renovation works of Kila Kothi | Chanderi | Culture | 30 | [6 empty] | DE under preparation. Target date shall be finalized after award of work.
|  | (b) | MADHYA PRADESH | SH:- C/o Jan Shaivhalay | Chanderi | Culture | 21 | [6 empty] | Detailed drgs under preparation by SA(CZ)
|  | (c) | MADHYA PRADESH | Sh:- Renovation of Baolies | Chanderi | Culture | 25 | [6 empty] | The work involve development of Ramnagar Talay. The Arch. Drgs are being prepared by SA(CZ)
| 237 |  | MADHYA PRADESH | Udasin Ashram Dronagiri, Chhatarpur, M.P. | Chhatarpur | Culture | 13.07 | 2004-06-01 | 2002-09-01 | 2003-01-01 | 2003-11-01 | 12.78 | 100 | For development work in and around Jain Mounment. Work is completed.
| 238 |  | MADHYA PRADESH | Jain Temple, Sonagiri MP | Sonagiri | Culture | 16.5 | 2002-09-01 | 2003-06-01 | 1903-12-01 | 2005-01-05 | 23.01 | 85 | Slow progress due to remoteness of site.
| 239 |  | MADHYA PRADESH | Jain Temple, Dhoodhai | Dhoodhai | Culture | 27.38 | 2002-02-01 | 2003-06-01 | 2004-01-01 | Dec'04 | 8.15 | 100 | Work completed.
| 240 |  | MADHYA PRADESH | Jain Temple, Chanderi, MP a) Phase-I | Chanderi | Culture | 54.91 | 2002-08-02 | 2002-11-01 | 2003-03-01 |  | 42.01 | 100 | Work consists of development work in and around Jain Mounment. Work is completed.
|  |  | MADHYA PRADESH | b) Phase-II | Chanderi | Culture |  | 2002-09-02 | 2003-01-01 | 2003-07-01 |  |  | 100 | Work consists of development work in and around Jain Mounment. Work is completed.
| 241 |  | MADHYA PRADESH | Jain Temple, Distt. Chhattarpur Nainagiri, MP | Nainagiri | Culture | 15 | 2002-06-01 | 2002-09-01 | 2003-01-01 | 2003-11-01 | 14.89 | 100 | Work consists of developmental work in and around Jain Monument. Work completed.
| 242 |  | MADHYA PRADESH | Paporaji, MP | Paporaji | Culture | 15 | 2002-06-01 | 2003-02-01 | 2003-08-01 |  | 12.74 | 100 | Work consists of developmental work in and around Jain Monument. Work awarded and shall be completed by 31/3/04.
| 243 |  | MADHYA PRADESH | Bawangaja, MP | Bawangaja | Culture | 24.71 | 2002-11-01 | 2003-08-01 | 2004-01-01 | 2004-10-01 | 6 | 35 | Slow progress due to remoteness of site and dealy in decision of temple management for demolition of compound wall and making available clear site.
| 244 |  | MADHYA PRADESH | Shreyansgiri, MP | Shreyansgiri | Culture | 24.9 | 2002-03-01 | 2002-05-01 | 2002-09-01 | 2004-06-01 | 8.35 | 80 | Full site is not handed over so far. The wok is completed on the part site handed over to CPWD except fixing of doors in facility centre.
| 245 |  | MADHYA PRADESH | Urvaha, MP a) Phase-I 25.18 | Urvaha | Culture | 56.73 | 2002-02-01 | 2002-06-01 | 2002-12-01 |  | 28.09 | 100 | Work consists of Facilitation and interpratation Centre, retaining wall, storm water drains and culverts, boundary wall, main gate and wicket gate, water supply system, horticulture work etc. Phase-I completed and Phase-II in progress affected due to remoteness of site.
|  |  | MADHYA PRADESH | b) Phase-II 31.55 | Urvaha | Culture |  | 2003-02-01 | 2003-10-01 | 2004-03-01 | 2004-09-01 |  | 25
| 246 |  | MADHYA PRADESH | Gandharapuri, MP | Gandharapuri | Culture | 4.5 | 2002-08-01 | 2002-06-01 | 2002-10-01 |  | 4.35 | 100 | Work consists of RCC structure for protection of idols lying in open. Work completed.
| 247 |  | MADHYA PRADESH | Archaeological Museum at Chanderi | Chanderi | Culture | 200 | 2002-12-01 | 2004-04-01 | 2005-06-01 | 2005-06-01 | 80.08 | 30 | Dealy in award due to dealy in issue of working drgs. By SA(HQ)II
| 248 |  | MADHYA PRADESH | Archaeological Museum at Shivpuri | Shivpuri | Culture | 200 | 2002-12-01 |  | - | - | - | - | The existing old museum has to be demolished to make way for C/o new Museum. The old museum bldg & land belonged to State Govt. which have been handed over to ASI only recently. Now permission of DG, ASI is awaited for demolition of the old building. Meanwhile working drgs. received and DE is under preparation.
| 249 |  | MADHYA PRADESH | Archaeological Museum at Khajuraho. | Khajuraho | Culture | 200 | 2002-12-01 | 2004-01-01 | 2005-04-01 | 2005-08-01 | 98.6 | 40 | Dealy in award due to dealy in issue of working drgs and recall of tender due to higher rates received in 1st call.
| 250 |  | MADHYA PRADESH | Jain Temple, Tiktoli | Tiktoli | Culture | 32.68 | 2003-04-01 | - | - | - | - | - | Temple management did not want work to be done as per provisions of sanction and wanted some other items of work instead. They made a reference to ministry which was not agreed to . Finally they have recently given clearence to take up the work as planned. The work site is of typical nature and is to be inspected before accord of T/S. DE under preparation.
| 251 |  | MADHYA PRADESH | C/o Jaiprakash Narayan Mahavidhylay (Distt. Morena) | Morena | Culture | 226.1 | 2003-02-01 | 2004-01-01 | 2005-03-01 | 2005-05-01 | 109.32 | 32 | Work in progress. Delay in award due to delay in issue of working drgs by SA(HQ).II
| 252 |  | MADHYA PRADESH | Redevelopment of areas around the western temple at Kharjuraho. SH: C/o cafetria bldg.) | Kharjuraho | Culture | 86.8 | 2004-03-01 | - | - | - | - | - | At present no targets can be fixed. The sanction of two works I.e. work and development of lake is yet to be received and the works are to be taken up only after the balance sanction for above two works is received to have over all impact. Detailed drgs under preparation by SA(HQ)II
| 253 |  | MADHYA PRADESH | Redevelopment of areas around the western temple at Kharjuraho. SH: c/o toilets cum ticket centre cum amenity centre.) | Kharjuraho | Culture | 45 | 2004-03-01 | - | - | - | - | - | -do-
| 254 |  | MADHYA PRADESH | Redevelopment of areas around the western temple at Kharjuraho. SH: c/o Bus and car parking 1 no. & battery operated vehicle.) | Kharjuraho | Culture | 59 | 2004-03-01 | - | - | - | - | - | -do-
| 255 |  | MADHYA PRADESH | Product infrasturcure and destination Development of Chanderi (MP) SH: Renovation works of Kila Kothi). | Chanderi | Culture | 30 | 2004-03-01 | - | - | - | - | - | DE under preparation. Target shall be finalized after award of work.
| 256 |  | MADHYA PRADESH | Product infrasturcure and destination Development of Chanderi (MP) SH: C/o Jan Shanchalaya) | Chanderi | Culture | 21 | 2004-03-01 | - | - | - | - | - | Tender invited.
| 257 |  | MADHYA PRADESH | Product infrasturcure and destination Development of Chanderi (MP) SH: Renovation of Baolies) | Chanderi | Culture | 25 | 2004-03-01 | - | - | - | - | - | The work involve development of Ramnagar Talay. The Arch. Drgs are being prepared by SA(CZ)
| 258 |  | MADHYA PRADESH | C/o Nirashrit Bhawan at Village Narawar Distt. Shivpuri. | Shivpuri | Culture | 43.93 | 2004-03-01 | - | - | - | - | - | PE submitted in 3/04, A/A &E/S awaited.
| 259 |  | MADHYA PRADESH | C/o Hall for Religious scriptures at Shri Digamber Jain Mandir Evam Dharamshala Sonagiri(MP) | Sonagiri | Culture |  |  | - | - | - | - | - | RE for Rs. 13.30 lacs sent in 1/2004. Sanction is awaited.
| 260 |  | MADHYA PRADESH | Development work at Shri Digamber Jain Atishay Kshetra, Barason (Purappattan Barneair) Distt Bhind I) C/o internal roads and paths and site developments, storm water drains etc. Chhatri premises. Ii) C/o RR masonry boundary wall with barbed wire fencing (4'x3") high about 350 meter length. | Bhind | Culture | 13.88 | 2004-03-01 | - | - | - | - | - | Tender invited.
| 261 |  | MADHYA PRADESH | C/o Balance work of Administration bldg for Instt for Hotel Management Catering Tech & Applied Nutrition at Maharajpur | Gwalior | Culture | 728.05 | 2001-02-01 | 2003-01-01 | 2004-06-01 | 2004-10-01 | 57.95 | 80 | Work in progress. Delay due to storage of funds due to which client asked for deferment of balance work. Progress also effected due to frequent chage in specification by consultant Arch. Engaged by client.
| 262 |  | MAHARASHTRA | Shri Chandraprabhu Bhavan, Bheloda | Bheloda | Culture | 25 | 8.3.02 | 2002-06-01 | 2004-03-01 | 2004-05-01 | 15.99 | 90 | Main work completed. Othe work in progress.
| 263 | 119 | MAHARASHTRA | C/o Guest House (5 Nos.) Dining Hall and Entry Plaza at 'T' Juction near Ajanta | Ajanta | Culture | 90.96 | 2003-03-01 | 2004-02-01 | 2004-05-01 | 2004-07-01 | 86.67 | 100 | Work completed.
| 264 | 116 | MAHARASHTRA | Integrated Development of western Circuit Development of Sindhudurg | Sindhudurg | Culture | 102.51 | - | - | - | - | 0.08 | - | Only limited scope of work can be taken up for which estimate are under preparation. (i) PE for recarpetting of roads upto Tarkarli. (ii) Approach road at Nanupal near Kalasi river sent to MTDC at Mumbai for sanction. Sr. Arch will be revising the drgs as desired by the Principal Sectt Min. of Tourism Govt. of Maharashtra. Devl works of parking & gardens being taken up at Singhdurg.
| 265 | 115 | MAHARASHTRA | Development of Vijaydurg | Vijaydurg | Culture | 200 | - | - | - | - | - | -
| 266 | 114 | MAHARASHTRA | Development of Jaigarh Fort | Jaigarh | Culture | 200.51 | - | - | - | - | 0.36 | -
| 267 | 9 | MAHARASHTRA | Dev. Of Foot hills at Ajanta Caves | Ajanta | Culture | 91.08 | 2003-05-01 | - | 2004-04-01 | 2004-12-01 | 51.69 | 76 | Work in progress. Work delayed due to restriction in transportation of material as well as storage. Funds transfer to Elect. (Rs. 10.00 lakhs)
| 268 |  | MAHARASHTRA | Addl. Works at T Junction | Ajanta | Culture | 8.52 | - | - | - | - | - | - | Work in progress.
| 269 | 17 | MAHARASHTRA | (a) C/o covered shelter for palkhi of Sant Gyaneshwar Maharaj retaining wall and prefabricated toilets to Varkaries at Saswad Distt Pune. | Pune | Culture | 93.62 | - | - | 2004-03-01 | 2004-07-01 | 5.28 | 90 | Work in progress.
|  |  | MAHARASHTRA | (b) Concrete pavement, ladies & gents toilets & approach road at Sopankaka Samadhi Mandir Saswad, Distt Pune. | Pune | Culture | - | - | - | 2004-03-01 | 2004-07-01 | 22.16 | 90 | Work in progress.
| 270 |  | MAHARASHTRA | (a) C/o covered shelter for palki of Sant Gyaneshwar Maharaj and providing other basic amenities to Varkaries at Jejuri Distt Pune. | Pune | Culture | 96.51 | - | - | 2004-05-01 | 2004-07-01 | 16.38 | 75 | Work in progress.
|  |  | MAHARASHTRA | (b) C/o Toilet, Renovation of Kitchen Hall and other amenities to Varkaries at Kirtan Sthal and Yatra Market Shtal at Jejuri Distt Pune | Pune | Culture | - | - | - | 2004-04-01 | 2004-07-01 | 31.9 | 90 | Work in progress.
| 271 | 4 | MAHARASHTRA | Development work around Loard Vitthal Temple at Pandharpur Distt., Solapur | Pandharpur | Culture | 494.6 | - | - | - | - | -
|  | 11 | MAHARASHTRA | (a) Palki Sohalla of Sant Gyaneshwar Maharaj, Alandi, Pune and Sant Tukaram Maharaj Dehu, Pune to Lord Vitthal Temple at Pandharpur SH: Providing water supply and toilet facilities to Varkaris at Vakhri, Near Pandharpur. | Pandharpur | Culture |  | - | 2004-06-01 | 2004-08-01 | - | 30.27 | 100 | Work completed
|  |  | MAHARASHTRA | (b) C/o covered shelter for Palkhi of Sant Gyaneshwar Maharaj, and Sant Tukaram Maharaj, and other amenities for Varkaris at Vakhri, Pandharpur | Pandharpur | Culture |  |  | 2004-02-01 | 2004-05-01 |  | 25.26 | 100 | Work completed
|  |  | MAHARASHTRA | (c) Development work around Sant Gyaneshwar Maharaj Temple at Alandi, Pune | Pandharpur | Culture
|  |  | MAHARASHTRA | (d) SH: C/o RCC covered Drainage channel on Bhagrathi Nallah. | Pandharpur | Culture |  |  |  | 2004-02-01 |  | 19.3 | 100 | Work completed
|  |  | MAHARASHTRA | (e) SH: C/o Toilets bloks & Tourist amenities in Alandi Nagar | Pandharpur | Culture |  |  |  | 2004-02-01 |  | 13.35 | 80 | Work in progress.
| 272 |  | MAHARASHTRA | Development works around Sant Tukaram Temple at Dehu | Pandharpur | Culture
|  |  | MAHARASHTRA | (a) SH C/o Toilet block Development of Ghat etc. | Pandharpur | Culture | [5 empty] | 3.64 | 100 | Work completed.
|  |  | MAHARASHTRA | (b) SH: C/o Darshan Mandpum | Pandharpur | Culture | [6 empty] | 75 | Work in progress.
| 273 | 32 | MAHARASHTRA | Development work Bhavanagar | Bhavanagar | Culture | 303.33 | 2002-11-01 | 2003-11-01 | 2004-11-01 | 2004-10-01 | 0.8 | 7 | Work in progress.
| 274 | 33 | MAHARASHTRA | Development work in Anand Jain Tirthsthan at Junagarh Gujrat | Junagarh | Culture | 186.45 | 2002-11-01 | 2003-12-01 | 2004-12-01 | 2004-12-01 | - | 2 | Work in progress.
| 275 | 34 | MAHARASHTRA | Development place for Sant Tukaram Temple at Dohi Civil amneities Pune | Pune | Culture | 100 | 2003-09-01
|  |  | MAHARASHTRA | a) C/o Darshan mandap & other misc work | Pune | Culture |  |  | 2004-02-04 | 2004-06-04 | 2004-06-04 | 35 |  | Work recently started.
|  |  | MAHARASHTRA | b) C/o toilet block, RCC bond Ghat development & other touriest amenities around Sant Tukaram Maharaj Devasthan | Pune | Culture |  |  | 2003-12-03 | 2004-03-04 | 2004-06-04 | 45 |  | Work in progress.
| 276 | 35 | MAHARASHTRA | Development work at Alandi, Pune | Alandi Pune | Culture | 100 | 2003-08-01
|  |  | MAHARASHTRA | a) Development of Bhagirathi Nallah | Alandi Pune | Culture |  |  | 2003-11-03 | 2004-02-01 |  |  | 100 | Work completed
|  |  | MAHARASHTRA | b) C/o toilet block, & other touriest amenities in Alandi i/c works at sidha bet | Alandi Pune | Culture |  |  | 2003-11-03 | 2004-02-01 |  |  | 80 | Work in progress.
|  |  | MAHARASHTRA | c) Provision of drinking water around the temple complex | Alandi Pune | Culture
| 277 | 36 | MAHARASHTRA | Refurbishment of Agha Khan Palace, Pune | Pune | Culture | 251 | 2003-10-01 | [5 empty] | Work completed.
|  |  | MAHARASHTRA | a) SH:C/o Composite stone masonry compound wall and UG sump. | Pune | Culture |  |  |  | 2004-02-04 |  | 15.08 | 100 | Work completed.
|  |  | MAHARASHTRA | b) SH: Road work and Black basalt stone pathways | Pune | Culture |  |  |  | 2004-01-04 |  | 26.17 | 100 | Work completed.
|  |  | MAHARASHTRA | c) SH: Horticulture water supply. | Pune | Culture |  |  |  | 2004-05-04 |  | 19.79 | 100 | Work completed.
| 278 |  | MAHARASHTRA | Leveling works, sewer lines, storm water drains, pre-cast blocks pavement, compound wall, road work, horticulture work, street lighting, pump with bore well, facilitation centre at Shri Dig Jain Parwarandir Bazargaon, Distt Nagpur | Bajargaon | Culture | 14.99 | 2002-08-01 | 2003-04-01 | 2003-12-01 |  | 8.8 | 100 | Work completed.
| 279 |  | MAHARASHTRA | Jain Temple Kolhapur | Kolhapur | Culture | 24.13 | 2002-08-01 | 2003-04-01 | 2004-01-04 |  | - | 100 | Work completed.
| 280 |  | MAHARASHTRA | Jain Temple Thair, Usmanabad | Thair | Culture | 25 | 2002-08-01 |  | 2003-07-01 | 2004-05-01 | 19.72 | 100 | Work completed in 4/2004.
| 281 |  | MAHARASHTRA | Jain Temple Kunthalgiri, Maharashtra | Kunthalgiri | Culture | 15 | 2002-08-01 | 2003-07-01 | 2004-04-01 | - | - | 100 | Work completed in 2/2004.
| 282 |  | MAHARASHTRA | Jain Temple Jamod | Jamod | Culture | 19.99 | 2002-08-01 | 2003-01-01 | 2003-05-01 | 2004-09-01 | 5.92 | 65 | Work in progress after recession of old contractor. Target date of completion is Mar'05.
| 283 |  | MAHARASHTRA | Shri Chandranath Swami Kasta Sangh Dig. Jain Temple Karanja, Distt Washim | Washim | Culture | 4.32 | 2002-11-01 | 2002-11-01 | 2003-02-01 | 2003-06-01 | 1.7 | 100 | Work completed. Site could not be finalized due to encroachment. Part encroachment is now removed. Architectural drawing under preparation.
| 284 |  | MAHARASHTRA | Facilitation centre with toilet block, Jain Temple Washim | Washim | Culture | 7.59 | 2003-01-01 | - | - | - | - | -
| 285 |  | MAHARASHTRA | Jain Temple Aurangabad. | Aurangabad | Culture | 25 | 2002-02-01 | 2003-08-01 | 2004-03-01 |  |  | 100 | Work completed.
| 286 |  | MAHARASHTRA | Development of works at Ellora Jain Caves No. 32 Aurangabad- 2600 years of Tirthankara Mahavir Janma Kalyanak. | Aurangabad | Culture | 76.88 | 2002-12-01 | - | - | - | 23.93 | - | Tender validity period lapse due to not receipt of approved drawings from DG, ASI tender to be recalled only after receipt of approval of drawing by DG, ASI New Delhi
| 287 |  | PUNJAB | Ludhiana Samaj ( Vanasthali) | Ludhiana | Culture | 15 | - | - | - | - | - | 100 | Work consists of Boundary with grill & horticulture. Work completed.
| 288 |  | PUNJAB | Bhagwan Mahavir Smarak (Vanasthali) Ludhiana. | Ludhiana | Culture | 166 | 30.3.03 | - | - | - | - | - | Work in progress.
| 289 |  | PUNJAB | Renovation of Jain temple at Buria. | Buria | Culture | 12.42 | 3.3.04 | - | - | - | - | - | NIT issued. Tenders are due to open on 18/6/04
| 290 |  | PUNJAB | Development of Saraswati Tirath, Pehowa. | Pehowa | Culture | 134.06 | 5.9.03 | - | - | - | - | - | Sanction not received.
| 291 |  | PUNJAB | C/o Boundary wall at Harsha Ka Tilla | Harsha ka Tilla | Culture | 55.46 | 2.7.02 | 3.8.02 | 2.12.02 | - | 41.15 | 95 | Work on the portion handed over to CPWD has been completed except 75 m wall which can not be completed due to land not given by ASI.
| 292 |  | PUNJAB | Development of Jain Temple at Ganour SH: Providing EI & Fans. | Ganour | Culture | 15 | 25.6.02 | - | - | - | 0.54 | 100 | Int. EI work completed.
| 293 |  | PUNJAB | Development of Bhagwan Mahavir memorial Vanasthali at Doraha, Ludhiana. | Ludhiana | Culture | 64.31 | 12.12.03 | 2004-05-01 | - | - | - | - | Work awarded levels are being taken at site. Elect. Work shall be taken up along with civil works.
38 | 294 |  | PUNJAB | C/o Tourist Complex at Kirat Pur Sahib | Kirat Pur | Tourism | 199.56 | - | - | - | - | - | - | A/A &E/S awaited.
| 295 |  | PUNJAB | C/o Food craft Instt. Anandpur Sahib. | Shaib | Culture | - | - | - | - | - | - |  | A/A &E/S awaited.
| 296 |  | PUNJAB | C/o IHM at Gurudaspur, SH: Girls Hostel for 28 Students(D/S) | Gurudaspur | Culture | 23.45 |  | 2004-05-01 | 2005-02-01 | 2005-02-01 | 7.69 | 50 | Work in progress.
| 297 | 153 | RAJASTHAN | Public Utility complex at Amer Fort, Hawa Mahal and Albert Hall | Amer | Culture | 54 | 2003-03-01 | 2004-04-01 | 2004-07-01 | 2004-09-01 | 0.54 | 35 | Work awarded.
| 298 | 155 | RAJASTHAN | Conservation and Restoration of Buland Darwaza, Chisti Dargah and Chhatries of Nagaur. | Nagaur | Culture | 103 | 2003-03-01 | - | - | - | - | - | Drawings awaited from RTDC.
| 299 | 156 | RAJASTHAN | Conservation Restoration and Development of Royal Cenotaph and Devi Bagh Sagar, Bikaner. | Bikaner | Culture | 90 | 2003-03-01 | - | - | - | - | - | Drawings awaited from RTDC.
39 | 300 | 151 | RAJASTHAN | Upgradation of Transport Terminal at (a) Mandawa (b) Mukundgarh (c) Nawalgarh | Mandawa, Mukundgarh, Nawalgarh | Tourism | 75 | 2003-03-01 | - | - | - | - | - | The consultant is M/s Wilber smith Associate Ltd. Appointed by RTDC, Jaipur. Drgs & BOQ received from RTDC for Nawalgarh, Mukundgarh and Mandawa. These have been discussed with RTDC and consultant by EE, Bikanerin 5/05. The Consultant has submitted modified drawings and estimates to RTDC again as per meeting held in July 2004.
40 | 301 | 152 | RAJASTHAN | Landscaping, plantation fencing illumination at (a) Fatehpur (b)Nawalgarh (c) Mandawa (d) Khimsar (e) Ramgarh (f) Dhundlod (g) Mukundgarh | Fatehpur, Nawalgarh, Mandawa, Khimsar, Ramgarh, Dhundlod, Mukundgarh | Tourism | 105 | 2003-03-01 | - | - | - | - | - | Drgs and BOQ not recd for Ramgarh, Fathepur, Nawalgarh, Dhundlod, Mukundgarh, Mandawa and Khimsar. Details yet to be received from RTDC.
41 | 302 | 154 | RAJASTHAN | Conservation of Nahargarh Fort, Jaipur | Nahargarh | Tourism | 100 | 2003-03-01 | - | - | - | - | - | Drawings awaited from RTDC.
42 | 303 | 146 | RAJASTHAN | General Lighting at Kumbalgarh | Kumbalgarh | Tourism | 33.6 | 2002-12-01 |  | - | 2004-06-01 | - | 80 | Fittings received at site, approval is still awaited from ASI, Jaipur
| 304 |  | RAJASTHAN | Development of works at Kumbhal Garh Fort (Raj) | Kumbhal Garh | Culture | 150 | 2003-07-01 | 2004-03-01 | 2004-05-01 | 2004-05-01 | 5.36 | 80 | Temple lighting- ASI approval awaited. All works of path lighting and illumination completed. Civil work completed.
| 305 | 147 | RAJASTHAN | Civil and Elect. Works for SEL at Kumbhal Garh | Kumbhal Garh | Culture | 89.36 | 2003-11-01 | -- | 2004-01-01 | 2004-01-01 | 6.89 | 100 | Work completed.
43 | 306 | 146 | RAJASTHAN | Civil & Elect. Works for SEL shows at Chittorgarh Fort. | Chittorgarh | Tourism | 70.75 | 2003-11-01 | 2004-06-01 | 2004-01-01 | 2004-04-01 | 8.8 | 100 | Work completed.
44 | 307 | 175 | RAJASTHAN | Landscape Development for Masuria Hills (Veer Durga Das Smarak) at Jodhpur. | Jodhpur | Tourism | 152.34 | 2003-11-01 | 2004-06-01 | 2005-03-01 | 2005-03-01 | - | - | Tenders invited on 07/06/2004 and under scrutiny. Tenders for electrical works reinvited.
45 | 308 | 152 | RAJASTHAN | C/o Vishhramshtali at Dargah Sharif at Ajmer | Ajmer | Tourism | 187 | 4.11.03 | 2004-07-01 | - | - | - | - | Drawings have been asked from SA, CPWD but he is busy in MAP drawings. Hence permission sought from ministry to get the drawings done from private Architects. Now drawings are taken up by SA and target date of all drawings given as 20/2004 Architectural drawings submitted to RTDC and client approval is awaited.
46 | 309 | 171 | RAJASTHAN | Dev. Of Chetak Samadhi, Rakt Talai, Badshahi Bagh at Haldi. | Haldi | Tourism | 227.56 | 13.11.03 | 2004-04-01 | 2004-10-01 | 2004-04-01 | 10.97 | 30 | ASI is already doing work. Hence work not to be done by CPWD. The work of Rakt Talai and Badshahi Bagh in progress. The work at Chetak Smarak abandoned after receiving instructions from ASI that this particular work is to be executed by Archeological Survey of India.
| 310 |  | RAJASTHAN | Panchin Digamber Jain Mandir, Viratnagar Jaipur (2nd Phase) | Jaipur | Culture | 68.59 | 10.3.03 | 2003-07-01 | 2004-02-01 | 2004-06-01 | 49.34 | 100 | Work completed and handed over.
| 311 |  | RAJASTHAN | Elect. Works. | Jaipur | Culture |  |  | 2003-08-01 | 2004-03-01 |  | 1.05 | 85 | Wiring work in progress. Work pending due to not availbility of DG set room by temple authority.
| 312 |  | RAJASTHAN | Pagaliaji Temple & Rishabdev Temple, Kesariyaji, Udaipur. | Udaipur | Culture | 125 | 2002-06-01 | 2002-07-01 | 2003-06-01 | 2003-08-01 | 31.59 | 100 | Work completed, final bill yet ot be paid.
| 313 | 1 | RAJASTHAN | Dev. of land approach Rd. drainage C.C. path at Rishab Deo Jain Temple, Udaipur. | Udaipur | Culture | 125 | 2002-04-01 | 2002-06-01 | 2002-09-01 | - | - | 100 | Work completed and handed over
| 314 |  | RAJASTHAN | Neminathji Jain Temple, Amer Jaipur. (2nd phase) | Jaipur | Culture | 67.94 | 2003-03-01 | 2003-07-01 | 2004-02-01 | 2004-02-01 | 47.28 | 100 | Work completed and handedover. Electrical work under progress.
| 315 |  | RAJASTHAN | Development of Jain Temple, Zawar Mines Udaipur. | Udaipur | Culture | 25 | 2002-02-01 | 2002-05-01 | 2002-09-01 | 2003-01-01 | 26.14 | 100 | Civil work completed. Elect work completed. Horticulture work needed to develop garden 1.0 lakh allocated from balance. Tender awarded recently.
| 316 |  | RAJASTHAN | Development of Achalgarh Jain Tirth, Mount Abu (2nd Phase) | Mount Abu | Culture | 25 | 8.3.02 | 1.6.02 | 10.9.02 | 31.1.03 | 27.82 | 100 | Work completed.
| 317 |  | RAJASTHAN | Development of Sh Shantinath Bhagwan Jain Mandir, Achalgarh, Sirohi, Mt. Abu (2nd Phase) ( Widening of balance path to Srinath/Adinath Temple.) | Mount Abu | Culture | 26.27 | 2003-03-03 | 2003-09-01 | 2003-12-01 | 2004-01-01 | 14.49 | 100 | Work completed.
| 318 |  | RAJASTHAN | Beautification and face lifting of Jain Temple, Amargsagar, Jaisalmer. Phase-I | Jaisalmer | Culture | 15 | 18.3.02 | 2002-06-01 | 2002-12-01 | 2003-03-01 | 13.29 | 100 | Work awarded on 31/8/04. The work is again held up on account of clearance from the trustee of Jain temple. The meting of trustees was held on 21/11/04 till date decision not conveyed by trust.
| 319 |  | RAJASTHAN | Beautification and face lifting of Jain Temple, Amargsagar, Jaisalmer. Phase-II | Jaisalmer | Culture | 5.08 | 10.3.03 | - | - | - | 0.76 | 100 | Work completed.
| 320 |  | RAJASTHAN | Development work at Jain Temple, Amar Sagar, Distt. Jaisalmer | Jaisalmer | Culture | 3.7 | 31.3.04 | - | - | - | - | - | A/A & E/S received during 4/2004. Tenders are being invited on 5/7/2004 and under scrutiny.
| 321 |  | RAJASTHAN | Development work at Shri Digamber Jain Atishay Kshetra Shri Parshnath Choolagiri a) Tuble Well with pipe line etc. b) Raising of compound wal & Fixing railing c) Road work C/o Rooms & Toilet for pligrims | Choolagiri | Culture | 15 | 31.3.04 | - | - | - | - | - | -
| 322 |  | RAJASTHAN | Development of Van Aushadhi Park at Shri Mahaveerji, Distt. Karoli (Phase-II) | Karoli | Culture | 67.5 | 10.3.03 | 2003-01-01 | 2004-08-01 | 2004-08-01 | 57.26 | 100 | Work completed. Tender are recalled for Bus stand and toilet block work.
| 323 |  | RAJASTHAN | Beautification and face lifting of Jain Temple at Ludarva, Jaisalmer. | Jaisalmer | Culture | 15 | 18.3.02 | 2002-06-01 | 2002-12-01 | - | 1.4 | 10 | All works were stopped in compliance of the directions given by Archeological Department. This matter has been taken up with Director General, Archeological Sruvey of India, New Delhi and with Ministry of Tourism at the time of visit of Hon'ble Minister Sh. Jagmohan. Now Superintendant ASI, Jaipur has intimated that some pockets for with NOC is not required and site has been checked for feasibility and pocket marked by ASI, Jaipur for construction activities are not the part of Jain Temple. Accordingly the tenders for work of carparking, recarpetting of road, railing for the park have been just awarded on 31/8/04. Elect work abandent due to ASI objection
| 324 |  | RAJASTHAN | Jain Temple at Dilwara temple, Mount Abu, Distt, Sirohi | Mount Abu | Culture | 300 | 2002-03-01 | - | - | - | 75.33 | - | The work was initially delayed because firstly the matter of permitting construction was subjudice in the Supereme Court of India and secondly the land for parking and public facilities was not handed over by the local administration. However, in 08/03 tenders for development works, near Kalpa Vriksha (the land for which is available) were invited sbject to clearance from Supreme Court and since the clearance was not obtained at that time so the tenders was rejected. Mean while a Public Interest Litigation (PIL) was field in the High Court against the invited tender and now stay was granted by its order dt 31/05/2004. The Supereme Court has allowed development works near Delwara Temple. The PIL which was due in High court at Jodhpur has since been dismissed in the hearing held on 23/7/04. certified copy of judgement is received. NIT for the work is under finalisation for call of tender. Work to be taken up after shifting of present shops. The SA (HQ)-II has been requested to finalise details of same for preparing DE/NIT.
| 325 |  | RAJASTHAN | Dev. of work at Jain Tirth, Ranakpur, Udaipur. SH: Sewerage treatment plant of 40000 ltr per day capacity, trees & landscaping (ph-III) | Ranakpur | Culture | 35 | 2003-03-01 |  |  |  | 15 | 35 | Work in progress.
| 326 |  | RAJASTHAN | Jain Temple at Tijara, Distt. Alwar (Phase-2nd) | Alwar | Culture | 69.03 | 10.3.03 | 16.9.03 | 2004-03-01 | 2004-03-01 | 50 | 100 | Work completed. Work under progress. Fans fittings held up as door not provided at site. DG set not required by clinet. It is being lifted from site.
| 327 |  | RAJASTHAN | Kumbhalgarh Fort SH: Electrification | Kumbhalgarh | Culture | 117.06 | 2002-11-01 | - | - | - | - | - | For installation of lighting in the Fort and related civil works. Work consists of spectator's gallery for light and sound show at Kumbhal Garh Fort, parking and approach road to main fort and electrification work of fort.
| 328 |  | RAJASTHAN | Development at Osian Town, Jodhpur | Jodhpur | Culture | 106.19 | 27.12.02 | 2004-06-01 | - | 2004-04-01 | 15.18 | - | Development plan for area around Jain tempels is under approval with Secy. M/o Tourism, Govt. of Raj. Elect work could not start due to land accquisition on process. Work heldup as the land is under dispute by locals. Matter is bing persued with administration.
| 329 |  | RAJASTHAN | Development work at Jain Mandir at Parshawnath Atishay Kshetra, Arhinda, Udaipur | Udaipur | Culture | 55.83 | 10.2.03 | 2003-07-01 | 2004-02-01 | 2004-04-01 | 42.92 | 100 | Work completed. For Horticulreu work tender awarded recently.
47 | 330 |  | RAJASTHAN | Integrated Development of Jaipur-Jodhpur-Jaisalmer-Bikaner-Shekhawati- Jaipur Tourist Circuit. | Jaipur / Jodhpur | Tourism | 644 | 2003-03-01 | -- | -- | -- | -- | -- | During the meeting held on 03/07/2003, it was decided that development plans will be prepared by RTDC.
48 | 331 | (i) | RAJASTHAN | Public Utility Complex at (a) Nahargarh (b) Fatehpur (c) Nawalgarh (d) Dhundlod (e) Mukundgarh (f) Mandawa (g) Kuchaman (h) Khimsar | Nahargarh, Fatehpur, Nawalgarh, Dhundlod, Mukundgarh, Mandawa, Kuchaman, Khimsar | Tourism | 92 | -- | 2004-06-01 | -- | -- | 2.78 | -- | The consultant is M/s Wilber smith Associate Ltd. Appointed by RTDC, Jaipur. Drawing and BOQ for Public Utility Complexex received from Tourism Department Rajasthan during 02/2004. The detailed estimates from consultant were discussed by EE, Bikaner during 05/05 with Sh. Anil Gupta, GM/ RTDC & the consultant. The consultant has submitted modified estimated to RTDC & CPWD. The RTDC has to approve modified drawings and specification to keep the cost within sanctioned amount. The RTDC has approved the same on 24/9/04. The tenders for civil work are being invited for each sanction seperatly and to opened on 24/12/2004.
|  | (ii) | RAJASTHAN | Signages | -- | Tourism | 25 | -- | 2004-06-01 | -- | -- | 0.75 | -- | Drawings and BOQ received. The consultant for this work is CRCI, New Delhi and they have been requested by EE, Bikaner in 05/2004 to finalise the structural drawings and resubmit BOQ for inviting tenders. The written matter for signage is still to be finalised by RTDC.
|  | (iii) | RAJASTHAN | Upgradation of Transport Terminal at (a) Mandawa (b) Mukundgarh (c) Nawalgarh | -- | Tourism | 75 | -- | -- | -- | -- | 2.25 | -- | The consultant is M/s Wilber smith Associate Ltd. Appointed by RTDC, Jaipur. Drawings and BOQ received from RTDC for Nawalgarh, Mukundgarh and Mandawa. These have been discussed with RTDC and consultant by EE, Bikaner in 05/05. The consultant has submitted modified estimates to RTDC and CPWD. The RTDC has to approve the modified drawings & specifications.
|  | (iv) | RAJASTHAN | Landscaping, plantation fencing illumination at (a) Fatehpur (b) Nawalgarh (c) Mandawa (d) Khimsar (e) Ramgarh (f) Dhundlod (g) Mukundgarh | Nawalgarh | Tourism | 105 | -- | -- | -- | -- | 3.15 | -- | Drawing and BOQ not received for Ramgarh, Fathepur, Nawalgarh, Dhundlod, Mukundgarh, Mandawa and Khimsar. Details yet to be received from RTDC.
|  | (v) | RAJASTHAN | Public Utility complex at Amer Fort, Hawa Mahal and Albert Hall | Jaipur | Tourism | 54 | 2003-03-01 | 2004-04-01 | 2004-06-01 | 2004-08-01 | 4 | 44 | Work in progress. Delaydue to late decision by consultant.
|  | (vi) | RAJASTHAN | Conservation of Nahargarh Fort, Jaipur | Jaipur | Tourism | 100 | 2003-03-01 | 2005-05-01 | -- | -- | -- | -- | Revised details from RTDC are awaited and tender recalled. Development works details awaited from RTDC.
|  | (vi) | RAJASTHAN | Conservation and Restoration of Buland Darwaza, Chisti Dargah and Chhatries of Nagaur. | Nagaur | Culture | 103 | -- | -- | -- | -- | -- | -- | The consultant for this work is CRCI, New Delhi. The details of conservation works have been submitted by consultant as per meeting held in June 2004 between consultant, RTDC and Director, Archeological and Museum, State of Rajasthan, Jaipur. RTDC is yet to be approve the conservation works. Details for development works are to be finalized by consultant in consultation with RTDC, Director, Archeological and Museum, State of Rajasthan, Jaipur.
|  | (vii) | RAJASTHAN | Conservation Restoration and Development of Royal Cenotaph and Devi Kund Sagar, Bikaner. | Bikaner | Culture | 90 | -- | -- | -- | -- | -- | -- | The consultant for this work is Ayojna School of Architect, Jaipur. Development drawing received for Royal Centoph and Devi Kund Sagar, Bikaner from RTDC. BOQ awaited, however these drawings are to be finalised by RTDC in consultant with Director Arachaeological and Museum, State of Rajasthan, Jaipur.
49 | 332 |  | RAJASTHAN | Integrated Development of Pushkar (Distt. Ajmer) in Rajasthan under destination development. | Pushkar | Tourism | 238.57 | 2003-11-01 | -- | -- | -- | -- | -- | RTDC has not given the approved drawnigs to CPWD. However estimate based on preliminary drawing are prepared by M/s Wilber Smith for selter pavellions and bus parking submitted to RTDC on 10/06/2004. Drawings for stadium are being finalised by the consultants for submission to RTDC. Approved working drawings awaited from RTDC for preparation of DE.
|  | (A) | RAJASTHAN | Dormitories for visitors at Mela Ground at Pushkar. | Pushkar | Tourism | 150 | 2003-11-01 | -- | -- | -- | -- | -- | -do
|  | (B) | RAJASTHAN | Stadium and tent platform at Pushkar. | Pushkar | Tourism | 74.48 | 2003-11-01 | -- | -- | -- | -- | -- | -do
|  | (C) | RAJASTHAN | Sulabh Sauchalaya Mela Ground at Pushkar. | Pushkar | Tourism | 14.09 | 2003-11-01 | -- | -- | -- | -- | -- | -do
50 | 333 |  | RAJASTHAN | Integrated devlopment at the Tourism Circuit from Adi Badri, Haryana to Dola Vira (Gujrat). | Hanumangarh | Tourism | 194 | 2003-11-01 | 2003-05-01 | -- | -- | -- | -- | The consultant for these works is HUDCO. Land yet to be acquired by Superintendant Archeologist. Work to be taken up after the land is available.
|  |  | RAJASTHAN | (a) C/o Archaeological Complex at Hanumangarh. | Hanumangarh | Culture | 52 | 2003-11-01 | 2003-05-01 | -- | -- | -- | -- | -do-
|  |  | RAJASTHAN | (b) C/o Archaeological Complex at Kalibanga. | Kalibanga | Culture | 52 | 2003-11-01 | 2003-05-01 | -- | -- | -- | -- | -do-
|  |  | RAJASTHAN | (c) C/o Archaeological Complex at Rangmahal. | Rangmahal | Culture | 90 | 2003-11-01 | 2003-05-01 | -- | -- | -- | -- | -do-
| 334 | 2 | RAJASTHAN | Dev. of work at Jain Tirth, Ranakpur, Udaipur. | Ranakpur | Culture | 130 | 2002-06-01 | 2002-08-01 | 2003-05-01 | 2004-02-01 | 153.77 | 100 | Work completed.
| 335 |  | RAJASTHAN | Protection work of Jaisalmer Fort. | Jaisalmer | Culture | 300.81 | - | - | - | - | - | - | Sanction awaited. PE sent to client dt. 11/2002
| 336 |  | RAJASTHAN | C/o Museum and office building for anthropological survey of India at Udaipur | Udaipur | Culture | 352.55 | 2002-12-01 | 2003-10-01 | 2005-08-01 |  |  | 40 | Work consists of c/o Museum and office bldg (both double storeyed RCC framed structure) having total plinth area of 4100 sqm. Structure is completed. Filler masonery walls and development work in progress.
| 337 |  | TAMILNADU | Development of infrastructure for Tourism in Kancheepuram | Kancheepuram | Culture | 259.4 | 2003-08-01 | 2004-02-01 | 2004-08-01 | 2004-08-01 | 72.05 | 60 | Work in progress. The work involved is c/o road side storm water drains. Recently the local body has requested for some changes in the original proposals and Ministry of Tourism has been requested to accord approval for the change. Out of 4680 metre 3330 metre brick work in Drain completed, 2260 metre lenght of RCC drain slab laid. Work at Kamarajar & Pachaiyappa street stopped for want of decision. work of Kamarajar steeet started during June 2004 only.
| 338 |  | TAMILNADU | Providing infrastructure facilities at Kancheepuram SH Pdg. High Mast Lighting. | Kancheepuram | Culture | 21 | 2003-09-01 |  |  |  |  | 20 | Work in progress.
| 339 |  | TAMILNADU | Providing lighting arraagement to group of monuments at Kancheepuram | Kancheepuram | Culture | 16.28
| 340 |  | TAMILNADU | C/o Youth Hostel at Ooty | Ooty | Culture | 124.5 | 2000-12-01 | 2004-04-01 | 2005-04-01 | 2005-04-01 | -- | 5 | Foundation work nearing completion.
| 341 |  | TAMILNADU | Holiday Home for Ooty | Ooty | Culture | 203.4 | 2000-02-01 |  |  |  | 10.83 | 95 | Work in progress.
| 342 | 170 | TAMILNADU | Development of Park near the Shore Temple Mahabalipuram | Kancheepuram | Culture | 299.93 | 2002-12-01 | 2003-03-01 | 2004-01-01 | 2004-01-01 | 220 | 100 | Work completed.
|  |  | TAMILNADU | a) Providing Landscape lighting | Mahabalipuram | Culture | -do- | -do- |  |  |  | 11.14 | 30 | Work in progress.
| 343 | 171 | TAMILNADU | Integrated Development of Mahabalipuram SH: Development near the five Rathas. | Mahabalipuram | Culture | 299.92 | 2002-12-01 | 2003-06-01 | 2004-06-01 | 2004-06-01 | 157 | 80 | Work in progress.
|  |  | TAMILNADU | a) C/o compound wall | Mahabalipuram | Culture | -do- | -do- | 2003-11-01 | 2004-03-01 | 2004-08-01 | 33.13 | 90 | Only three sides were handedover by the client deptt and hance completed the balance northern side boundary is handed over by the client in 6/2004 and which is in progress.
|  |  | TAMILNADU | b) 101 Shops (civil) | Mahabalipuram | Culture | -do- | -do- | 2003-09-01 | 2004-03-01 | 2004-08-01 | 85.87 | 100 | Work completed
|  |  | TAMILNADU | c) Ticket booth, Bus shelter, toilet and restaurant. | Mahabalipuram | Culture | -do- | -do- | 2003-11-01 | 2004-03-01 | 2004-09-01 | 9.32 | 45 | Roof slab of restaurant and kiosk completed. Centring and shuttering for toilet foof and ticket counter progress.
|  |  | TAMILNADU | d) Parking and roads | Mahabalipuram | Culture | -do- | -do- | 2004-01-01 | 2004-04-01 | 2004-09-01 | 28.71 | 35 | 50% of the footpath completed. The remaining portion consolidation of earth for parking lot in progress. The road ending to five rathas could not be taken up till end of April as the clearance from the revenue deptt was give by 5/04. Now the base concrete for road is in progress.
|  |  | TAMILNADU | e) Pdg. Int EI & Fans | Mahabalipuram | Culture | -do- | -do- |  |  |  | 1.15 | 40 | Work in progress
|  |  | TAMILNADU | f) Pdg. Landscape lighting | Mahabalipuram | Culture | -do- | -do- |  |  |  | 14.75 | 30 | Work in progress
| 344 |  | TAMILNADU | Dev. of Mahabalipuram under destination dev. Programme. SH: Area dev. Of shore temple at Mahabalipuram C/O Compound wall, shops and site dev. Shore temple. | Mahabalipuram | Culture | 199.82 | 2002-02-01 | 2003-01-01 | 2003-07-01 | 2003-12-04 | 225.18 | 100 | Work in completed.
| 345 |  | TAMILNADU | Jain Temple, Thoraipadi, Villupuram, Tamil Nadu | Thoraipadi, | Culture | 10.44 | 2002-08-01 | 2004-03-01 | 2004-05-01 | 2004-07-01 | 7.03 | 60 | Out of total sanction the work like CC pavement around temple, pump house 200 litres capacity elevated RCC tank, toilet block 2 nos., Horticulture work and borewell were completed. Presently the work of compound wall is in progress at the instruction of client deptt. letter dt. 10/12/03 in the savings available which was not contemplated originally.
| 346 |  | TAMILNADU | C/o Yatri niwas at Thiruvannamalai | Thiruvannamalai | Culture | 45.37 | 3/2004 | -- | -- | -- | -- | -- | Approval received recently. Preparation of Detailed drgs and D E in progress.
| 347 |  | TAMILNADU | Additional and alterations to NAI Bldg at Pondicherry | Pondicherry | Culture | 2.5 | -- | -- | -- | 2004-07-04 | -- | -- | Work in progress and are programmed for completion in July-04
| 348 |  | TAMILNADU | Procurement of land and C/o Resdl qtr for the staff of the Andaman and Nicobar Regional Centre, Port Blair | Port Blair | Culture | -- | -- | -- | -- | -- | -- | -- | The requirements of the Andaman & Nicobar Regional Centre of ASI have been considered while planning GPRA at Port Blair which has been completed. Officers and staff of ASI have already been allotted with accommodation of GPRA at Port Blair. Under the circumstances there appears to be no necessity to have a separate pool of quarters for ASI at Port Blair.
| 349 |  | TAMILNADU | C/o Yatri Niwas at Rameshwaram | Rameshwaram | Culture | [6 empty] | 100 | Work completed.
| 350 |  | TAMILNADU | C/o Tourist Complex at Salem | Salem | Culture | 4.14 |  |  |  |  | 4.47 | 100 | Work completed.
| 351 |  | TAMILNADU | C/o Tourist Lodge at Namakkal | Namakkal | Culture | 3.19 |  |  |  |  | 2.56 | 100 | Work completed.
| 352 |  | TAMILNADU | C/o Yatri Niwas at Srirangam | Srirangam | Culture | 2 | [6 empty] | Work not started.
| 353 |  | TAMILNADU | Providing flood lights to Vivekananda Rock at Kanyakumari | Kanyakumari | Culture | 32.13 | [6 empty] | Work not started.
| 354 |  | TAMILNADU | C/o Addl bldg for IHCMT at CIT Campus, Taramani, Chennai SH: Pdg. Int. E.I. & Fans | Taramani | Culture | 203 |  |  |  |  | 7.28 | 45 | Work in progress.
51 | 355 | 184 | UTTAR PRADESH | Integrated development of Vaishali Nalanda-Varanasi Buddist Circuit. | Nalanda-Varanasi | Tourism | 295 | 2002-12-01 | -- | -- | 2004-06-01 | 10.98 | -- | Work in progress.
|  |  | UTTAR PRADESH | (a) Development of Dhammachakk appavattana Sarnath | Sarnath | Tourism | 72.05 | 2003-11-01 | 2004-02-01 | 2004-05-01 | 2004-12-01 | 44.99 | 92 | Work in progress.
52 |  | 183 | UTTAR PRADESH | (b) Development /Landscapping around Maharani Laxmi Bai Varanasi | Varanasi | Tourism | 90 | -- | -- | -- | -- | -- | -- | This project has been deleted from sacntion scope of work Vide M/o T&C No. 5-PNE(5)/2002 dt. 4/11/03.
|  |  | UTTAR PRADESH | (d) Development of land around Chaukhandi Stupa at Varanasi. | Varanasi | Tourism | 90.23 | 2003-04-01 | -- | -- | 2003-12-01 | 47.7 | 100 | Work completed in 12/03.
53 | 356 | 89 | UTTAR PRADESH | C/o Interpretation Centre/ Shopping Centre, Fatehpur Sikri Agra | Agra | Tourism | 495.8 | 2003-09-01 | 2003-05-01 | 2004-05-01 | 2004-12-01 | 47.69 | 80 | Architectural drawings are yet to be issued by HUDCO. Based on the drawings, cost of the work will be worked out and approval obtained from ASI Ministry.
| 357 |  | UTTAR PRADESH | Development of works at Digamber Jain Kshetra Shoripur, Bateshwar | Bateshwar | Culture | 29.56 | 2003-03-01 | 2003-01-01 | 2004-04-01 | 2004-04-01 | 22.65 | 100 | Work completed. Final bills to be paid.
54 | 358 |  | UTTAR PRADESH | Development & Beautification of Ram Ki Paidi in Ayodhya, Faizabad | Ayodhya | Tourism | 98.18 | 2003-11-01 | -- | -- | 2004-08-01 | -- | -- | Site has not yet been handed over by Irrigation Department Govt. of UP.
| 359 |  | UTTAR PRADESH | Development & upgradation of education facilities at Sitabdiara, Distt.- Balia. | Sitabdiara (Balia) | Culture | 102.97 | 26/11/02 | -- | -- | 2004-06-01 | -- | 100 | Work completed.
|  |  | UTTAR PRADESH | a) C/o 8 No. teachers qtr. | Sitabdiara (Balia) | Culture | -- | -- | -- | -- | -- | 86.12 | 100 | Work completed.
|  |  | UTTAR PRADESH | b) C/o 30 Bedded Girls Hostel | Sitabdiara (Balia) | Culture | -- | -- | -- | -- | -- | -- | 100 | Work completed.
|  |  | UTTAR PRADESH | c) Provision of furnitures. | Sitabdiara (Balia) | Culture | -- | -- | -- | -- | -- | -- | 100 | Work completed.
|  |  | UTTAR PRADESH | d) Water proofing treatment & repair work for GGI College. | Sitabdiara (Balia) | Culture | -- | -- | -- | -- | -- | -- | 100 | Work completed.
|  |  | UTTAR PRADESH | e) Elect. Works. | Sitabdiara (Balia) | Culture | -- | -- | -- | -- | -- | 5.62 | 100 | Work completed.
| 360 | 14 | UTTAR PRADESH | Renovation of Jain Temple at Varanasi | Varanasi | Culture | 123.49 | -- | -- | -- | 2004-03-01 |  | 100 | Work completed.
|  |  | UTTAR PRADESH | (a) Development work at three birth places of Jain Thithankaras in Varanasi Birth Place of Suparasnath at Bhadaini | Bhadaini | Culture | 43.3 | 2002-11-01 | 2003-03-01 | 2003-10-01 | 2004-12-01 |  | 98 | Work in progress.
|  |  | UTTAR PRADESH | (b) Brith Place of Parashwanath Bhelupur | Bhelupur | Culture | 30.64 | -- | 2003-03-01 | 2003-07-01 | 2004-01-01 |  | 100 | Work completed and handed over in Jan'2004
|  |  | UTTAR PRADESH | (c) Birth Place of Shreyansnath at Sarnath | Sarnath | Culture | 49.35 | -- | 2003-03-01 | 2004-09-01 | 2004-12-01 | -- | 77 | Work in progress.
|  |  | UTTAR PRADESH | Electrical works Birth Place | Sarnath | Culture | -- | -- | -- | -- | 2004-08-01 | 2.56 | 70 | Slow progress due to chage of site for library.
| 361 |  | UTTAR PRADESH | C/o Cultural Complex at Chowkaghat, Varanasi. | Varanasi | Culture | 334.08 | 2002-10-02 | 2003-01-01 | 2004-01-01 | 2004-12-01 | 175.91 | 98.5 | U.P.State Govt. released Rs.50.00Lacs only as matching fund . Total funds received only 250 Lacs. VDA to give LOP for Development Works. Work in progress. Casting of RCC folded plate & front lobby roof completed. External stone cladding in progress. RCC flooring completed, Plaster/Flooring work in officer/toilets completed. Tile work in toilets completed. Fabrication of door/window in progress. Elect. Sub-station Ist floor slab in progress. Work in progress.
|  |  | UTTAR PRADESH | a) Elect. Works. | Varanasi | Culture | -- | -- | -- | -- | 2004-11-01 | 0.80
| 362 |  | UTTAR PRADESH | Dudhai | Dudhai | Culture | 25 | -- | -- | -- | -- | -- | -- | Work consists of facilitation center, cement concrete pathway, boundary wall, tube well etc. Tender are being invited. Facilitation ceter, CC pavement, boundary wall, tube well, internal water supply etc.
| 363 |  | UTTAR PRADESH | Sironji | Sironji | Culture | 20 | -- | -- | -- | -- | -- | 100 | Work completed.
| 364 |  | UTTAR PRADESH | Vehlana | Vehlana | Culture | 19.34 | -- | -- | -- | -- | -- | 100 | Work consists of Parking space, CC pavement horticulture work, development of gardens etc. Work completed.
| 365 |  | UTTAR PRADESH | Hastinapur | Hastinapur | Culture | 14.8 | -- | -- | -- | -- | -- | 100 | Work completed.
| 366 |  | UTTAR PRADESH | Badagaon | Badagaon | Culture | 24.92 | -- | -- | -- | -- | -- | -- | Work consists of Bitument macadam for pot holes repairs, premix carpeting for 5 km. length of the road, horticulture work etc.
| 367 | 16 | UTTAR PRADESH | Documentation-cum-History Centre at Shahid Smark, Balia. | Ballia | Culture | 276.99 | 2002-12-01 | 2003-08-01 | 2004-05-01 | 2005-02-01 | 162.73 | 75 | Work stopped due to shooting of 4 workers at site. Now, it is resumed & in progress.
55 | 368 |  | UTTAR PRADESH | Redevelopment of Rajendra & Dashashwamedh Ghat at Varanasi. | Varanasi | Tourism | 29.12 | 2003-11-01 | 2004-05-01 | 2004-08-01 | 2005-01-01 | 0.13 | 5 | Initially the work delayed due to flooding in river Ganga. Work started.
| 369 |  | UTTAR PRADESH | Signages | Varanasi | Tourism | 5 | -- | -- | -- |  |  |  | Signages will be done after Dharm Chakra Pravartan Park will be completed.
| 370 |  | UTTAR PRADESH | Miscellaneous Works for pdg. Finishing, approach road, W/S Scheme Toilet facilities etc. for various sites under Patna Circle of A.S.I. | Patna | Culture | 152.16 | 2003-03-03 | - | - | - | - | - | DE is being framed. Drgs. To be prepared by HUDCO funds not deposited by ASI. Tenders to be called after deposit of funds.
| 371 |  | UTTAR PRADESH | Protection work of Jain Shwetamber Temple at Chandrawati, Varanasi, UP. | Varanasi | Culture | 542.16 | - | - | - | - | - | - | PE sent on 29.1.03. But sanction not received.
| 372 |  | UTTAR PRADESH | C/o Cultural Complex at Varanasi. SH: Open Air Theatre. | Varanasi | Culture | 36.39 |  | - | - | - | - | - | PE sent on 2.10.02. But sanction not received.
| 373 |  | UTTAR PRADESH | Pdg. Air Conditioning & false ceiling in Museum at Sarnath, Varanasi. | Varanasi | Culture | 80.10 | 2003-11-03 | - | - | 2004-12-01 | - | - | This is mainly AC work which is in progress. Tenders for civil works called.
| 374 |  | UTTAR PRADESH | Elect. Works. | Varanasi | Culture | 61.00 | - | - | - | - | - | -
| 375 |  | UTTAR PRADESH | Development of park in memoray of J.P. in Sitabdiara, Distt.- Balia. | Ballia | Culture | 15.00 | 2004-01-04 | - | - | - | - | - | RPE amounting to Rs. 26.22 lacs sent to M/s Tourism & Culture on 20/7/04.
| 376 |  | UTTAR PRADESH | Additional work in J.P. Memorial House at J.P. Nagar, Balia. | Ballia | Culture | 16.69 | 2003-11-01 | - | - | - | - | - | Tenders recalled as no tender recd. In first 2 calls. Tenders in 3rd call accepted.
| 377 |  | UTTAR PRADESH | C/o Bhojpuri Cultural Centre at Shaheet Smarak Park, Basantpur, Ballia. | Ballia | Culture | 100.00 | 2004-02-04 | - | - | - | - | - | Tender received and opened on 29/10/04.
| 378 |  | UTTAR PRADESH | C/o Pt. Udai Shankar Academy of Dance & Music at Almorah (SH: C/o Museum & Auditorium). | Almorah | Culture | 486 | 2003-03-01 | 2004-04-04 | 2005-10-01 | 2005-10-01 | 62.5 | 31 | Scope of work was reduced from Rs.6.5 Crore to Rs.5 Crore by Ministry. Another estimate for balance scope of the work costing around Rs.One Crore would be submitted. Decision is to be taken whether the same can be submitted to Ministry of Tourism / Culture. The building can not be put to use without sanctioning the estimate for left out of work.
56 | 379 | 12 | UTTAR PRADESH | C/o Great green Vista at Haridwar (Ph-I) | Haridwar | Tourism | 202.5 | 2004-04-01 |  |  |  | 236 | 100 | Work completed.
|  |  | UTTAR PRADESH | C/o Great Vista at Haridwar (Ph-II) | Haridwar | Tourism | [7 empty] | Govt. of Uttranchal has to ensure that dispute over work site with Govt. of UP is sorted out. They have to confirm that the work can be taken up and there will be no hold up on work on this account.
|  |  | UTTAR PRADESH | a) P/F precast jali, glazed door, windows, benches & finishing work | Haridwar | Tourism | 12.5 | 2004-04-01 | 2004-05-01 | 2004-07-01 | 2004-11-01 | 3.5 | 100 | Work completed.
|  |  | UTTAR PRADESH | b) C/o Parking near cannal bridge at Haridwar. | Haridwar | Tourism | 90 | 2004-04-01 |  |  | 2005-03-01 |  |  | Assurance has been given by District Authorities for site. Tenders have been invited and to be received by 29-12-04.
|  |  | UTTAR PRADESH | C/o Parking near Anand Van Samadhi | Haridwar | Tourism | 20 | 2004-04-01 |  |  | 2005-03-01 |  |  | -do-
|  |  | UTTAR PRADESH | Repair/ painting/ finishing of 3 Nos bridges over cannal. | Haridwar | Tourism | 10 | 2004-04-01 | [5 empty] | -do-
|  |  | UTTAR PRADESH | C/o Kumbh stabmbh at Haridwar | Haridwar | Tourism | 5.36 | 2004-03-01 | 2004-05-01 | 2004-07-01 | 2004-11-01 | 2.5 | 80 | Work in progress.
57 | 380 |  | UTTARANCHAL | Landscape development plan for Guest House & near vacinity area at Rishikesh. | Rishikesh | Tourism | 493 | 2002-12-01 |  |  |  | 3.5 |  | Work held up
| 381 | 180 | UTTARANCHAL | Landscape development plan near Alakhnanda Guest House at Haridwar- Rishikesh. | Haridwar | Culture | 493 | 2002-12-01 | 2003-10-01 | 2003-12-01 | 2004-01-01 | 46 | 100 | Fittings installed. S/C not taken by Tourism Deptt of Uttaranchal.
|  | (a) | UTTARANCHAL | Development of Great Green Vista at Haridwar. | Haridwar | Tourism | 394 | 2002-12-01 | 2003-04-01 | 2003-11-01 | 2004-03-01 | 233.41 | 100 | Work completed
|  | (b) | UTTARANCHAL | C/o Development work along Gange river bank at Rishikesh Ph-I. | Rishikesh | Culture | 59.5 | 2004-04-01 |  |  |  | 69.53 | 100 | Work completed
|  |  | UTTARANCHAL | b) C/o Land scaping parking & development along Ganga river at Rishikesh Ph-II | Rishikesh | Culture
|  |  | UTTARANCHAL | I) Renovation of Ghat on the left bank of Ganga River. | Rishikesh | Culture | 40 | 2004-04-01 |  |  | 2005-03-01 |  |  | Tender under process.
|  |  | UTTARANCHAL | ii) Grassing of lawn. | Rishikesh | Culture | 2 | 2004-04-01 | 2003-11-01 | 2003-11-01 | 2004-12-01 |  | 45 | Work in progress.
| 382 |  | UTTARANCHAL | C/o National Instt. Of Hotel Management, Centring & Nutrition at Dehradun. | Dehradun | Culture | 637 | 2003-03-01 | 2004-04-01 | 2005-10-01 | 2005-10-01 | 93.6 | 23 | Foundation complete. Superstructure in progress. Additional deposite required.
| 383 |  | UTTARANCHAL | C/o Udai Shankar Acadamy for Dance & Music at Almorah (SH: C/o Museum & Auditorium) | Almorah | Culture | 486 | 2003-03-01 | 2004-04-01 | 2005-10-01 | 2005-10-01 | 172 | 35 | Work in progress. Additional deposit required.
| 384 | 15 | UTTARANCHAL | C/o Youth Hostel at Badrinath Dham, Badrinath. | Badrinath | Culture | 165.91 | 2002-03-01 | 2003-10-01 | 2005-04-01 | 2005-04-01 | 0.47 | - | Work in progress. Modified LOP finalised on 9/6/04.
|  |  | UTTARANCHAL | a) Bridge across Alaknada at Badrinath | Badrinath | Culture | 148 | 2003-10-01 | [5 empty] | Position of bridge is finalized in 9/04 and soil investigation is in process.
|  |  | UTTARANCHAL | b) C/o Approach road from Shri Badrinath to Mana village | Badrinath | Culture | 42.5 | 2003-10-01 | 2004-07-01 | 2004-11-01 | 2004-11-01 | 0.11 | 30 | Work in progress
|  |  | UTTARANCHAL | c) Shed nearing parking at Shri Badrinath | Badrinath | Culture | 51.8 | 2003-10-01 | 2004-05-01 | 2004-09-01 | 2004-10-01 | 26 | 90 | Work in progress
| 385 | 19 | WEST BENGAL | C/o Anthropological Survey of India office cum Museum Bldg. Complex at Salt Lake, Kolkata. | Kolkata | Culture | 533.73 | 2000-10-01 | 2001-07-01 | 2003-07-01 | 2004-12-01 | 203.34 | 99 | Work held up for want of fund.
| 386 | 20 | WEST BENGAL | C/o Bhasha Bhawan for National Library at Kolkata | Kolkata | Culture | 7703 | 2002-05-01 | 1995-01-01 | 2003-09-01 | 2004-03-01 | 5073.52 | 100 | All wokrs completed. Handing over.
| 387 |  | WEST BENGAL | Interior Decoration, Furniture & furnishing of Bhasha Bhawan for National Library at Kolkata SH: P/I of Compactors and stacks at varius floors. | Kolkata | Culture | 382 | 2002-10-01 | 2003-07-01 | 2004-03-01 | 2004-03-01 | -do | 100 | All wokrs completed. Handing over.
| 388 |  | WEST BENGAL | Interior Decoration, Furniture & furnishing of Bhasha Bhawan for National Library at Kolkata SH: P/I of office furniture SH: P/I of Additional compactors. | Kolkata | Culture | 178 | 2003-01-01 | 2003-07-01 | 2004-03-01 | 2004-03-01 | -do | 100 | All wokrs completed. Handing over.
| 389 |  | WEST BENGAL | Restoration & upkeeping of Maulana Abdul Kalam Azad Institute of Asian Studies at 5, Asraf Mistry Lane | Kolkata | Culture | 57.1 | 2002-09-01 | - | - | - | - | - | -
|  |  | WEST BENGAL | a) SH:- Bldg. Portion ( Strl. Pt Ph-I) | Kolkata | Culture | - | - | 2003-09-01 | 2004-06-01 | 2004-07-01 | 13 | 100 | Work completed.
|  |  | WEST BENGAL | b) SH:- Bldg. Portion (Interior works) | Kolkata | Culture | - | - | 2004-08-01 | 2004-09-01 | 2004-09-01 | - | 50
|  |  | WEST BENGAL | c) SH: Bulk Services(Civil) | Kolkata | Culture | - | - | 2004-07-01 | 2004-09-01 | 2004-09-01 | - | 40
| 390 |  | WEST BENGAL | C/o Office Bldg. & Hostel Block at Plot NO- 18-199, Salt Lake, Kolkata for Moulana Abul Kalam Institute. | Kolkata | Culture | 579 | 2004-01-04 | 2004-04-01 | 2005-10-01 | 2005-10-01 | - | - | Arch drgs. submitted to local body for approval in Jun-04 Aproval awaited. DE/NIT to be prepared on receipt of detailed arch drgs.
Jharkhand